Project Plan Document

CareConnect

University of Maryland Global Campus

SWEN 670 - Software Engineering Capstone

Dr. Mir Assadullah

Aug 30th, 2025

Contributors: Summer 2025 class and Fall 2025 class.

Table of Contents

LIST OF TABLES	vi

LIST OF FIGURES	vii

Revision History	viii

1.	Executive Summary – (updated in v4.0)	9

1.1	Project Name- (inherited from v3.0)	9

1.2	Purpose – (updated in v4.0)	9

1.3	Scope – (updated in v4.0)	9

1.4	Document History and Acknowledgments-(added in v4.0)	10

2.	Document Conventions (Definitions, Acronyms, and Abbreviations)- (added in v4.0)	10

3.	Objectives and Goals	13

3.1	Goals – (inherited from v3.0)	13

3.2	Objectives – (inherited from v3.0)	13

4.	Scope of Work - (updated in v4.0)	13

4.1	In-Scope – (inherited from v3.0 with new additions in v4.0)	13

4.1.1	User Management and Access	13

4.1.2	Communication Integration	13

4.1.3	Tasking & Medication Management – (updated v4.0)	14

4.1.4	Health Data Logging and Tracking – (updated in v4.0)	14

4.1.5	Wearables Integration	14

4.1.6	Note, Documentation Application, & Patient Assistant for Telemedicine – (updated in v4.0)	14

4.1.7	Emergency Assistance	15

4.1.8	Gamification	15

4.1.9	Billing & Subscription Management – (updated in v4.0)	15

4.1.9.1	Invoice-Bill Assistant (New) – (added in v4.0)	15

4.1.9.1.1	Intake	15

4.1.10	Scheduling & Notifications	16

4.1.11	Analytics & Reports	16

4.1.12	AI Integration	16

4.1.13	Multilingual Support – (updated in v4.0)	16

4.1.14	Virtual Check-In Rounds–(added in v4.0)	16

4.1.15	Mood & Affect Monitor–(added in v4.0)	17

4.1.16	Security, Privacy, Consent, & Data Handling – (added in v4.0)	17

4.1.17	Audit Logging and Data Retention	17

4.1.18	Mail Delivered Assistant (USPS Informed Delivery Integration)- (added in v4.0)	17

4.1.18.1	Electronic Visit Verification (EVV) – (added in v4.0)	18

4.1.18.2	Home Monitoring Integration/ Smart Home integration– (added in v4.0)	18

4.1.18.3	Patient Assistant Telemedicine/Notetaker – (added in v4.0)	18

4.1.18.4	Patient Calendar Assistant – (added in v4.0)	19

4.2	Out-of-Scope – (updated in v4.0)	19

4.2.1	Clinical Diagnosis	19

4.2.2	Accessibility Enhancements	19

4.2.3	Advance Home Automation	19

4.2.4	Custom Medical Device Development	19

4.2.5	Public Social Media Integration	19

4.2.6	Community Forums	19

4.2.7	Hardware Integrations – (added in v4.0)	20

4.2.8	Insurance Adjudication Systems – (added in v4.0)	20

4.2.9	In-App Purchases for Subscription Billing – (added in v4.0)	20

5.	Stakeholders - (updated in v4.0)	20

5.1	Internal: - (updated in v4.0)	20

5.2	External: – (updated in v4.0)	20

6.	Timeline & Milestone – (updated v4.0)	21

6.1	Timeline and Milestone Table	21

6.2	Gantt Chart – (updated in v4.0)	22

7.	Technical Architecture– (updated in v4.0)	23

7.1	Architectural Objectives – (inherited from v3.0)	23

7.2	Logical System Architecture – (updated in v4.0)	24

7.3	High-Level System Architecture Diagram- (updated in v4.0)	26

7.4	Architectural Rationale-(updated in v4.0)	27

7.5	Runtime Flows – (updated in v4.0)	28

7.6	Technology Stack Summary – (inherited from v3.0)	29

7.7	Deployment Topology Highlights – (inherited from v3.0)	30

7.8	Frontend – (updated in v4.0)	30

7.9	Backend- (updated in v4.0)	31

7.10	Database – (inherited from v3.0)	33

7.11	APIs – (Updated in v4.0)	34

7.11.1	Fitbit Web API	34

7.11.2	Apple HealthKit API	34

7.11.3	Google Health Connect API	35

7.11.4	Google Smart Device Management (SDM) API	35

7.11.5	Alexa Smart Home Skill API	35

7.11.6	OpenFDA API	35

7.11.7	DeepSeek AI API (added in v4.0)	35

7.11.8	USPS Informed Delivery API	36

7.12	AI Services – (updated in v4.0)	36

7.12.1	Purpose and User Flow – (updated in v4.0)	36

7.12.2	Technical Architecture	36

7.12.2.1	Frontend Integration	36

7.12.2.2	AI Gateway	36

7.12.2.3	DeepSeek Service	36

7.12.2.4	Review & Escalation	37

7.12.2.5	Security and data Protection	37

7.12.2.6	Compliance and Governance	37

7.12.2.7	Summary and Future Enhancements	37

7.12.2.7.1	AI Service Summary	37

7.12.2.7.2	Future Enhancements	37

7.13	Hosting – (inherited from v3.0)	37

7.13.1	Cloud Deployment Model	37

7.13.2	Containerization and Orchestration	37

7.13.3	Serverless-First & Scale-to-Zero	38

7.13.4	Security and Reliability	38

7.14	Security	38

7.14.1	Data Protection	38

7.14.1.1	Encryption	38

7.14.1.2	Data Minimization	38

7.14.2	Authentication and Access Control	38

7.14.2.1	User Authentication	38

7.14.2.2	Role-Based Access Control (RBAC)	39

7.14.2.3	Principle of Least Privilege	39

7.14.3	Secure APIs	39

7.14.3.1	API Gateway Protection	39

7.14.4	Infrastructure Hardening	39

7.14.4.1	Network Isolation	39

7.14.4.2	Web Application Firewall (WAF)	39

7.14.4.3	Firewall Rules	39

7.14.5	Monitoring and Logging	39

7.14.5.1	Real-Time Monitoring	39

7.14.5.2	Audit Logging	39

7.14.6	Vulnerability Management	39

7.14.6.1	Interval Scanning	39

7.14.6.2	Automated Patching	40

7.14.7	Compliance Measures	40

7.14.7.1	Regulatory Compliance	40

7.14.7.2	Data Retention and Deletion	40

8.	Project Deliverables- (updated in v4.0)	40

8.1.1	Upcoming Milestones (New Deliverables)	41

9.	Risk & Mitigation- (updated in v4.0)	42

9.1	Risk Probability Matrix - (inherited from v3.0)	42

9.2	Risk Identification, Probability, and Mitigation- (updated in v4.0)	42

10.	Budget Estimate-(updated in v4.0)	44

10.1	Labor Cost- (updated in v4.0)	44

10.1.1	Team Labor Cost Breakdown by Milestones- (added in v4.0)	44

10.1.1.1	Milestone 1: Weeks 1-3	44

10.1.1.2	Milestone 2: Weeks 4-6	45

10.1.1.3	Milestone 3: Weeks 7-9	45

10.1.1.4	Milestone 4: Weeks 10-12	46

10.2	Materials Cost-(inherited from v3.0)	46

10.3	Infrastructure Cost – (updated in v4.0)	46

10.3.1	AWS Core Services – (inherited from v3.0)	50

10.3.2	Third-party / One-time Fees- (updated in v4.0)	50

10.3.3	Total Budget for MVP Phase (13 weeks ≈ 3 months)	50

10.3.4	Cost-Control & Optimization Plan – (inherited from v3.0)	51

10.3.5	Alignment to Financial Policies	51

10.3.6	Budget Summary for Project Plan- (updated in v4.0)	51

10.4	Risk Buffer – (added in v4.0)	52

11.	Roles & Responsibilities – (updated in v4.0)	52

11.1	Roles	53

11.2	RACI Matrix	54

12.	Monitoring and Reporting – (updated in v4.0)	56

12.1	Objectives	56

12.2	Intra-Team Monitoring and Reporting	56

12.3	Project Communications	57

12.3.1	Internal Meetings	57

12.3.2	Internal-External Meetings	57

12.3.3	Cross-Team Meetings	57

12.3.4	Quality and Risk Reporting	57

12.4	Quality Plan	57

13.	Assumptions - (updated in v4.0)	58

14.	Constraints - (updated in v4.0)	58

15.	Work Breakdown Structure (WBS) - (updated in v4.0)	59

15.1	Structure	59

Trigger Detection Module: Evaluates transcripted patient interactions for key phrases and escalates caregiver alerts with audit log updates.	60

16.	Change Management Procedures - (updated in v4.0)	60

16.1	Change Control Process - (updated in v4.0)	60

16.2	Change Control Board Roles - (updated in v4.0)	63

16.3	Internal Change Requests - (updated in v4.0)	64

16.4	External Change Requests - (updated in v4.0)	64

16.5	UI/UX Wireframe Preview - (inherited from in v3.0)	64

16.6	Change Request Form - (added in v4.0)	65

17.	Appendices - (updated in v4.0)	65

17.1	Glossary of Terms	65

17.2	References	67

18.	Appendix A: Project Decision Tracker	68

18.1	Team  – A Decision Tracker	69

18.2	Team  – B Decision Tracker	69

18.3	Team  – C Decision Tracker	70

18.4	Team – D Decision Tracker	70

-

# LIST OF TABLES

Table 1 Definitions, Acronyms, and Abbreviations	10

Table 2 Milestone and Timeline Table	21

Table 3 Architectural Objectives Table	23

Table 4 Logical System Architecture Table	23

Table 5 Architectural Rationale Table	27

Table 6 Technology Stack Summary Table	29

Table 7 Risk Probability Matrix Table	42

Table 8 Risk Probability and Mitigation Table	42

Table 9 Budget Estimate for Total (Teams A-D) Labor Costs	44

Table 10 Team Labor Cost Breakdown Milestone 1	44

Table 11 Team Labor Cost Breakdown Milestone 2	45

Table 12 Team Labor Cost Breakdown Milestone 3	45

Table 13 Team Labor Cost Breakdown Milestone 4	45

Table 14 Infrastructure Cost Table	48

Table 15 Fees Table	49

Table 16 Total Infrastructure Table	49

Table 17 Cost-Control Table	50

Table 18 Budget Summary Table	51

Table 19 Roles & Responsibilities Table with Assigned Team Members	52

Table 20 RACI Matrix Table Key:	53

Table 21 Change Control Board Members	63

# LIST OF FIGURES

Figure 1 Gantt Chart of Milestones for CareConnect Project	23

Figure 2 High-Level System Architecture Diagram 1 (NEW)	27

Figure 3 High-Level System Architecture Diagram 2	27

Figure 4 Change Control Process Flow	66

# Revision History

| Team Name | Date | Reason for Changes | Version |
| --- | --- | --- | --- |
| CareConnect Team Summer 2025 | 05/31/2025 | Initial document submission. | 1.0 |
| CareConnect Team Summer 2025 | 06/14/2025 | Revisions based on 1.0 feedback | 2.0 |
| CareConnect Team Summer 2025 | 07/26/2025 | Revisions based on 2.0 feedback | 3.0 |
| CareConnect Team Fall 2025 |  | 08/30/2025 |  | Restart Revision: Re-baselined schedule, updated budget, refined scope based on current assessment. Incorporated all prior work from |  | 4.0 |  |
| CareConnect Team Fall 2025 |  | 9/13/2025 |  | Revisions based on 4.0 feedback |  | 4.1 |  |
| CareConnect Team Fall 2025 | 10/14/2025 | Revisions based on 4.1 feedback | 4.2 |

# Executive Summary – (updated in v4.0)

## Project Name- (inherited from v3.0)

The name of this project is CareConnect.

## Purpose – (updated in v4.0)

The purpose of the CareConnect project is to develop a comprehensive, secure, and AI-enhanced mobile platform that revolutionizes collaborative care. It moves beyond simple connection to become a centralized ecosystem that empowers caregivers and patients by intelligently automating administrative tasks, deriving insights from health data, and facilitating communication across the entire care journey.

This application aims to enhance the quality, safety, and efficiency of care by providing tools that:

- Capture Critical Information: Utilize AI-powered note-taking to transcribe medical conversations (both telemedicine and in-person) and transform physical mail into accessible digital data.

- Derive Actionable Insights: Monitor patient well-being through mood analysis and structured health tracking, presenting trends and alerts to caregivers.

- Automate Coordination: Manage medications with intelligent reminders, consolidate appointments into a shared calendar, and streamline the processing of medical bills.

- Ensure Security and Accessibility: Operate on a foundation of strict HIPAA and GDPR compliance, with offline functionality and an accessible design for users of all abilities.

Ultimately, CareConnect fosters a proactive, informed, and collaborative care environment that reduces administrative burden, minimizes errors, and strengthens the patient-caregiver relationship.

## Scope – (updated in v4.1)

The scope of the CareConnect platform encompasses a unified digital ecosystem for collaborative care. The system is in scope to include:

Core Functionality:

- AI-Powered Assistance: Real-time transcription for medical calls/visits (with speaker ID), ADA mail digitization via OCR, and mood monitoring.

- Health Management: Symptom, meal, and medication tracking (CRUD with reminders), and a collaborative calendar with AI-assisted scheduling. Additionally, it will include camera fall detection.

- Trigger Detection: Caregivers can select predefined or add custom phrases that are flagged during note transcription within the Documentation and Patient Assistant module to generate caregiver alerts.

- Platform Infrastructure: Secure, role-based authentication, unified patient/caregiver dashboards, and integrated messaging/video calls.

- Administrative Tools: OCR-based medical bill processing/payment and subscription billing management.

- Other Integrations: Alexa and vial of life.

The system is out of scope for:

- Providing diagnostic medical advice or interpreting health data.

- Directly controlling medical devices (integrations are for data ingestion only).

- Functioning as a full clinical electronic health record (EHR).

## Document History and Acknowledgments-(added in v4.0)

This Project Plan builds upon the significant work completed by the previous project team [Summer 2025]. Their contributions, including the initial scope definition, architectural analysis, and risk assessments, form the foundation of this document. Version 4.0 focuses on re-baselining the project schedule, updating resource allocations, and refining the scope to align with current strategic objectives. Any version thereafter will be a representation of the revisions and contributions of the current team [Fall 2025].

# Document Conventions (Definitions, Acronyms, and Abbreviations)- (updated in v4.1)

# Table 1 Definitions, Acronyms, and Abbreviations

| Term | Definition/Description |
| --- | --- |
| AC | Acceptance Criteria – Specific conditions that a feature or deliverables must satisfy to be accepted |
| ADLs | Activities of Daily Living – Basic patients care tasks (e.g. eating, dressing, bathing) tracked within CareConnect |
| AI | Artificial Intelligence – Technologies enabling automated reasoning, natural language processing and predictive analytics (e.g. Ask AI, mood detection) |
| API | Application Programming Interface – A set of defined rules enabling communication between software components. CareConnect uses REST/GraphQL APIs for integration |
| APP | Application – Refers to the CareConnect mobile/web application |
| ASL | American Sign Language – Automated text-to-sign-language conversation feature to improve accessibility |
| AWS | Amazon Web Services – Cloud provider used for hosting, storage, security, and serverless architecture |
| BA | Business Analyst – Role responsible for gathering requirements, stakeholder communication, and requirements traceability |
| BFF | Backend-for-Frontend – API layer that aggregates microservice calls to optimize app performance |
| CI/CD | Continuous Integration / Continuous Deployment – Automation pipeline for testing, building, and deploying software |
| CSV | Comm-Separated Values – File format used for data export and reporting |
| DB | Database – Structured data store; CareConnect uses AWS RDS PostgreSQL, DynamoDB, and Timestream. |
| DevOps | Development & Operations – Practices for automating software delivery, infrastructure and monitoring. |
| DR | Disaster Recovery – Process to restore systems and data after outages; includes backups and multi-region failover. |
| ECS | Elastic Container Service – AWS service used to orchestrate CareConnect’s microservices . |
| EHR | Electronic Health Record (implied from context in Section 1.4, though not explicitly defined in the acronym list). |
| ETL | Extract, Transform, Load – Data integration process, implemented in CareConnect with AWS Glue for analytics. |
| EVV | Electronic Visit Verification -- A computerized system that uses smart devices to capture electronic proof of when and where a home or community-based service visit began and ended. |
| FHIR | Fast Healthcare Interoperability Resources – Industry standard for exchanging healthcare data (future integration consideration). |
| GDPR | General Data Protection Regulation – EU regulation for personal data protection, relevant to privacy compliance. |
| HIPAA | Health Insurance Portability and Accountability Act – U.S. regulation for safeguarding Protected Health Information (PHI) . |
| IaC | Infrastructure as Code – Practice of provisioning/managing infrastructure using code (e.g., Terraform, AWS SAM) . |
| IAM | Identity and Access Management -- AWS service for managing permissions and access to AWS resources. |
| JSON | JavaScript Object Notation – Lightweight data-interchange format used for APIs and configurations. |
| JWT | JSON Web Token – Token-based authentication mechanism used in AWS Cognito and API Gateway . |
| KMS | Key Management Service – AWS service for managing cryptographic keys and encryption. |
| KPI | Key Performance Indicator -- Indicator that helps to gauge performance and progress. |
| LLM | Large Language Model (implied from context in Section 7.12, though not explicitly defined in the acronym list). |
| MFA | Multi-Factor Authentication – Security feature requiring multiple verification methods (e.g., password + code). |
| MRC | Monthly Recurring Cost – Budgeting metric used in project cost tracking . |
| MSK | Managed Streaming for Apache Kafka – AWS service for event-driven messaging between CareConnect services . |
| MVP | Minimum Viable Product – Initial functional version of CareConnect with essential features . |
| NDC | National Drug Code – Unique identifier for medications; used in integration with OpenFDA API . |
| NLP | Natural Language Processing -- AI techniques used to interpret, classify, or extract meaning from text data. |
| PHI | Protected Health Information – Sensitive patient health data regulated under HIPAA . |
| PII | Personally Identifiable Information – Any data that could identify an individual (e.g., name, SSN). |
| PL | Project Lead – Role accountable for project oversight, schedule, and deliverables . |
| QA | Quality Assurance – Ensures deliverables meet defined quality standards through testing and validation . |
| RBAC | Role-Based Access Control – Security principle where access is based on user roles . |
| RACI | Responsible, Accountable, Consulted, Informed – Responsibility assignment matrix for project tasks . |
| REQ | Requirement – A documented functional or non-functional specification . |
| RPO | Recovery Point Objective -- The maximum targeted period in which data might be lost due to a system outage. |
| SLA | Service Level Agreement (implied from context in Section 10.3, though not explicitly defined in the acronym list). |
| SRS | Software Requirements Specification – Defines CareConnect’s system requirements and constraints . |
| TLS | Transport Layer Security – Protocol for encrypting data in transit (v1.3 used in CareConnect) . |
| UAT | User Acceptance Testing – Final validation phase where end users verify the system meets requirements . |
| UI | User Interface – Front-end design and interaction layer of CareConnect. |
| USPS | United States Postal Service. |
| UX | User Experience – The overall usability, accessibility, and satisfaction experienced by users . |
| WAF | Web Application Firewall -- A firewall that protects against common web exploits. |
| WBS | Work Breakdown Structure – Hierarchical decomposition of project deliverables . |

# Objectives and Goals

## Goals – (inherited from v3.0)

The goal of the project is to build an intuitive interface where users can easily understand the application and effortlessly navigate through it.

## Objectives – (inherited from v3.0)

The objective of the project is outlined below:

- Provide an integrated platform where patients and caregivers can connect, coordinate, and communicate.

- Provide all the necessary tools for caregivers to manage, track, and support their care recipients.

- Provie all the necessary tools for the patient to manage their daily health tasks and activate emergency alerts at the time of need.

# Scope of Work - (updated in v4.1

The scope of the CareConnect project is to design, develop, and deploy a comprehensive, mobile-first care coordination platform for iOS and Android. The application will serve as a unified digital hub connecting caregivers and patients, enhancing quality of care through efficient monitoring and management of health-related activities.

The platform's functionality is expanded to include not only core health tracking but also invoice and billing management, enhanced communication features, AI-powered assistants, and home monitoring capabilities. The application will be developed using modular architecture with Flutter/Dart for the front end and AWS for backend services.

This scope is defined by the deliverables listed below. All functionalities not explicitly mentioned are considered out-of-scope for the current project phase.

## In-Scope – (inherited from v3.0 with new additions in v4.0)

### User Management and Access

- The application shall allow caregivers to register, log in, and create a profile using email and password.

- The application shall allow caregivers to manage patient profiles.

### Communication Integration

- The system shall support in-app messaging, audio/video calling, and virtual check-in rounds.

### Tasking & Medication Management – (updated v4.0)

- The application shall allow caregivers to assign daily tasks to patients (such as medication and meal reminders).

- The application shall allow patients to mark the task complete.

- The system shall support Create, Read, Update, and Delete (CRUD) operations for medication lists.

- The system shall provide reminders for scheduled doses.

- The system shall prepare for future integration with pharmacy systems.

### Health Data Logging and Tracking – (updated in v4.0)

- The application shall allow caregivers and patients to manually record health data (e.g., vital signs) and generate reports for review.

- The application shall store data in a structured format for reporting and analytics.

### Wearables Integration

The system shall integrate with external health data platforms (Fitbit, Apple HealthKit, Google Health Connect) to ingest patient activity and vital data.

The system shall store imported data in a structured format and present it alongside manually entered health records for reporting and analytics.

### Note, Documentation Application, & Patient Assistant for Telemedicine – (updated in v4.0)

- The application shall allow caregivers to share notes related to their care recipient(patient).

- The application shall transcribe speech to text for patient/care recipient incoming calls (e.g., cellular, FaceTime) and save notes locally on the patient/care recipient device.

- The application shall have speaker identification/diarization that distinguishes the Patient/Care Recipient, Caregiver, and other speakers in the transcript.

- The application shall have a caregiver-managed exception list of phone numbers that are never transcribed.

- The application shall have trigger detection: caregiver can select predefined or add custom phrases (e.g., “schedule an appointment with,” “I am going to prescribe,” “I want you to go to”) to flag within notes and generate alerts.

- The application shall have sensitive data detection: alert the caregiver if PII such as SSN or Medicare numbers is detected in notes.

- The application shall allow patients and caregivers to search by keyword across transcribed call notes.

- The system shall sort by date and group notes by subject category.

- American Sign Language (ASL) interpretation is available during telemedicine/checkup calls for Patient/Care Recipients who need it.

- The system shall require consent and compliance: present and record user consent; feature availability is subject to device OS capabilities and applicable call-recording laws.

### Emergency Assistance

- The application shall allow patients to activate an emergency signal, notifying caregivers and SOS during urgent situations.

### Gamification

- The application shall have Badges, rewards, motivation messages, and compliance leaderboards. These features will enhance user engagement by recognizing consistent activity and promoting healthy behaviors through in-app visuals.

### Billing & Subscription Management – (updated in v4.0)

The application shall support subscription-based billing for caregivers, including the ability to define pricing tiers (e.g., $20/patient/month), activate subscriptions upon user onboarding or patient linking, and securely collect payment via credit card or PayPal using Stripe integration.

Subscription Payment for IOS Devices – (added in v4.0)

- The system shall integrate with Stripe Web to process payments securely on IOS devices using Payments Links to comply with IOS In App Purchase Policy.

#### Invoice-Bill Assistant (New) – (added in v4.0)

##### Intake

- The application shall capture invoices/bills via camera or uploaded image; support upload of online bills.

- The system use AI/LLM parsing to extract key attributes (e.g., provider, patient, dates, services/products, amounts, payment status/indicators, QR/payment links) into JSON.

- The system shall support on device models where feasible to facilitate offline processing.

###### Review and Data Quality

- The system shall present populated invoice forms for manual entry/edit, review, confirm, and save; require a “No Edit” confirmation when applicable.

###### Storage and Organization

- The system shall store extracted attributes to a relational database.

- The system shall provide dashboard views and capabilities to organize, search, and filter by provider, patient, date of service, services/products, and payment status types (e.g., Pending, Sent, Paid, Pending payment from insurance, Rejected by insurance).

###### Payment Facilitation and Record Keeping

- If a payment link is present, the system shall open the provider’s payment page. If not, enable use of third party payment apps (e.g., Stripe) or link to an installed mobile banking app to complete payment externally.

- The system shall allow users to mark invoices as paid and recording payment confirmation details (e.g., amount, confirmation number, paid date).

- The system shall allow user to generate mock checks and letters to support insurance claims as needed.

### Scheduling & Notifications

- The system shall allow caregivers to create both template-based and custom care tasks and deliver alerts and reminders via push notifications, email, or SMS based on user preferences and priority.

- The system shall allow caregiver shifts to be scheduled, updated, and viewed, including assignment of start/end times and shift reminders.

### Analytics & Reports

- The system shall generate real-time dashboard metrics and shall allow export of health and care data in CSV or PDF format for external reporting or consultation purposes.

### AI Integration

The system shall include AI-powered features such as:

- Ask AI: An assistant that answers health-related queries using the patient’s records.

- Mood Detection: Real-time emotion analysis during video calls using on-device facial and voice recognition.

- These features shall include disclaimers and links to the original data sources

### Multilingual Support – (updated in v4.2)

- The System shall include multilingual capabilities to support users from diverse linguistic backgrounds.

- The System shall enable users to switch the language in the app ensuring the accurate appropriate translation.

- The system shall launch in English.

- The system shall prepare for additional languages, including Spanish, Farsi, Amaharic, and Arabic.

- The system shall use the flutter_localizations library to ensure accurate translation and localization support.

### Virtual Check-In Rounds–(added in v4.0)

- The system shall support daily or weekly caregiver-patient check-ins.

- The system shall provide care givers’ manual entry options and structured Q&A forms.

- The system shall use AI to analyze voice or text during check-ins to assess mood.

### Mood & Affect Monitor–(added in v4.0)

- The system shall use AI models to detect emotional state from patient input.

- The system shall display mood results over time in graphs.

- The system shall connect mood results to wellness tracking features.

### Security, Privacy, Consent, & Data Handling – (added in v4.0)

- The system shall encrypt all patient health data in storage and during transfer.

- The system shall require patient or caregiver consent before using voice or text for AI analysis.

- The system shall comply with HIPAA and GDPR regulations.

- The system shall require explicit patient or caregiver consent before using voice or text for AI analysis.

- The system shall employ a role-based access and caregiver-patient linking with appropriate permissions.

- The system shall require explicit consent flows for any audio capture, transcription, and analysis.

- The system shall employ a non-diagnostic stance and disclaimers: outputs are informational and do not constitute medical advice.

### Audit Logging and Data Retention

The system shall log all critical actions such as note transcription, billing updates, EVV submissions, and payment activities for compliance and traceability.

The system shall enforce data retention and deletion policies in accordance with HIPAA and GDPR requirements.

### Mail Delivered Assistant (USPS Informed Delivery Integration)- (added in v4.0)

- The system shall parse the user’s USPS Informed Delivery Daily Digest email from their inbox (with user permission) and extract relevant details (e.g., sender, mailpiece summary, package tracking numbers, expected delivery dates, action links).

- The system shall capture mailpiece images via the phone camera and use on-device OCR to extract key information for accessible display.

- The system shall provide ADA-friendly presentation using the mobile OS’s built-in accessibility features (e.g., font scaling) and clear, high-contrast layouts aligned to OS settings.

- The system shall deep-link to USPS actions (e.g., tracking updates, delivery instructions, schedule redelivery) on USPS sites/apps.

- The system shall allow users to set reminders/notifications for expected deliveries and notable mailpieces.

#### Electronic Visit Verification (EVV) – (added in v4.0)

- The system shall capture clock-in and clock-out times for caregivers via mobile devices.

- The system shall log all location data (GPS coordinates) compliance.

- The system shall aggregate and submit EVV visit data to the state aggregator API for certification.

#### Home Monitoring Integration/ Smart Home integration– (added in v4.0)

- The system shall be able to link to cameras and smart devices in the care recipient's home to monitor the care recipient.

- AI shall be used to detect events like a fall and alert the care giver.

#### Patient Assistant Telemedicine/Notetaker – (added in v4.0)

- The system shall use speech to text conversion with diarization to identify speakers and provide a script of the conversation.

- Notes will automatically be generated from video and phone calls unless the calling number was manually excluded.

- Notes can also be generated by a user manually enabling a recording during in person conversations.

- AI will be used to detect personally identifiable information (PII), important dates, and customizable trigger words. Trigger words will perform and associated action setup by the user.

- The system shall also translate the generated text into American sign language (ASL).

- When PII is detected the care giver will be notified, when AI detects an important date it will add it to the calendar, and both the care giver and recipient will be notified.

- Note scripts will be stored on the user’s local device with functionality to sort by date, group by subject, and search notes by keywords.

#### Patient Calendar Assistant – (added in v4.0)

- The system shall have a calendar visible to both the care giver and care recipient.

- The care giver and care recipient shall be able to manually enter new events, tasks and reminders.

- Events will also be added to the calendar by AI recognizing important dates in note files on the user's local device. Users will be notified when an AI generated date is added.

- The system shall display notifications when events are approaching at a time interval before the event decided by the user.

- The system shall keep a record of completed tasks and past events after they are removed from the active list of reminders.

## Out-of-Scope – (updated in v4.0)

### Clinical Diagnosis

- The system shall not offer medical diagnosis or prescribe treatments. AI features are strictly informational with required disclaimers.

### Accessibility Enhancements

- The application shall not include features such as voice control, screen reader compatibility, or high-contrast mode.

### Advance Home Automation

- Only essential triggers (e.g., motion alerts) are in scope. Full smart home automation routines (e.g., lighting, climate control) are excluded.

### Custom Medical Device Development

- The project shall not involve creating new wearables or sensors. Integration is limited to existing APIs and platforms.

### Public Social Media Integration

- The application shall not support public social media integration such as Facebook or

Twitter cross-posting.

### Community Forums

- The application shall not include open community forums or large-scale public networking features.

### Hardware Integrations – (added in v4.0)

- No dedicated hardware (scanners, biometric devices) will be bundled. Only standard device cameras/scanners are supported.

### Insurance Adjudication Systems – (added in v4.0)

- Full claims adjudication, insurance eligibility verification, or direct EDI integration with insurers is out-of-scope. Only basic claim letter generation is included.

### In-App Purchases for Subscription Billing – (added in v4.0)

- Direct use of Apple In-App Purchase (IAP) APIs for subscription payments will not be supported; instead, Stripe web redirection will be used.

# Stakeholders - (updated in v4.0)

## Internal: - (updated in v4.0)

The Internal Stakeholders involved in this project are listed below. The details about the roles and responsibilities of the internal stakeholders are outlined in Section 10 of this document.

- Client / Product Owner

- Project Mentor

- MS Teams & GitHub Mentor

- Class Project Manager

- Team Leads

- Technical Lead/Architect

- AI/ML Specialist

- Security & Compliance Lead (New: Essential for HIPAA, GDPR, and PCI DSS requirements across all teams)

- Software Developers

- Lead Business Analyst

- Business Analysts

- Lead UI/UX Designer

- UI/UX Designers

- Lead Tester

- Testers (including specialized Security Penetration Testers) (Enhanced: To validate financial and health data security)

## External: – (updated in v4.1)

The following are the key external stakeholders for the CareConnect project:

End Users:

- Patients/Care Recipients: End users who manage health tasks, receive reminders, and use AI features (note-taking, mail assistant).

- Caregivers: Individuals who manage patient schedules, tasks, wellness data, and review AI-generated notes and alerts.

  - Billing Coordinator (New)(added in v4.1): A trusted caregiver or family member delegated by the patient to view medical invoices and update their payment status (e.g., paid, disputed, sent to insurance) within the system.

- Family Members: Extended family who support care and may have secondary, read-only access to stay informed.

Professional & Advisory:

- Health Professionals: Licensed providers who may use CareConnect for remote monitoring and coordination of care tasks.

- Accessibility & ASL Consultants (New: Required to validate Team A's ASL and accessibility features)

- Clients/Mentors: Advisors providing project development feedback.

- University Faculty (Professor): Faculty overseeing and evaluating the capstone project.

Platform, API & Regulatory Providers:

- App Distributors: Apple App Store, Google Play Store.

- Cloud & AI Service Providers: AWS (hosting), Google Cloud AI / AWS Transcribe (AI models), Twilio.

- Financial Service Providers: Stripe, Apple/Google.

- OCR & Hardware Integration Providers: Google Vision API / Adobe PDF Services (bill scanning - Team D), IoT Camera manufacturers.

- USPS API Administrators

- Compliance Auditors (HIPAA/GDPR/PCI DSS) (New: External auditors may be needed to verify compliance for launch).

# Timeline & Milestone – (updated v4.0)

## Timeline and Milestone Table

Table 2 Milestone and Timeline Table

| Milestone | Deliverables Due | Due Date |
| --- | --- | --- |
| Milestone 1 | - Project Plan - Software Requirements Specification | August 30th, 2025 |
| Milestone 2 | - Technical Design Document - Software Test Plan | September 13th, 2025 |
| Checkpoint | PowerPoint of Progress |  |
| Milestone 3 | - Code - Programmer Guide - Deployment and Operations Guide | October 25th, 2025 |
| Milestone 4 | - User Guide - Test Report | November 4th, 2025 |

Note. This table outlines the major milestones and deliverable due dates for the CareConnect project.

## Gantt Chart – (updated in v4.1

Figure 1 Gantt Chart of Milestones for CareConnect Project

Note. This table outlines the major milestones and deliverable due dates for the CareConnect project.

This Gannt chart offers a clear, visual overview of the entire project timeline. It helps identify what is currently in progress, what is coming next, and what has been completed. It complements our written schedule by making the plan easier to understand at a glance, and it will also serve as a living reference for future updates and progress tracking.

An external Microsoft Project file has been included as a supplement of the overall documents for a more detailed view of the CareConnect project Gantt chart.

# Technical Architecture– (updated in v4.0)

The purpose of this section is to translate the functional and non-functional requirements defined in the SRS into an implementable, cloud-native architecture. It explains how

CareConnect’s caregiver/patient features, especially Billing & Subscription Management and Analytics & Reporting—will be realized on AWS using Flutter, Spring Boot micro-services, and managed platform services. The accompanying deployment and system architecture diagrams visualize component boundaries, data flow, and runtime hosting topology.

## Architectural Objectives – (inherited from v3.0)

Table 3 Architectural Objectives Table

| Objective | Rationale |
| --- | --- |
| Scalability | Must support adding thousands of patients without downtime while ingesting real-time wearable data. |
| Regulatory Compliance | HIPAA/GDPR drive our choices for encryption, audit logging, and isolated VPC design. |
| Time-to- Market | The eleven-week delivery window requires managed services (Fargate, Cognito, MSK) to minimize ops toil. |
| Cost- Efficiency | MVP phase should remain <$300 / month; autoscaling and spot pricing mitigate idle spend. |
| Extensibility | Event-driven, domain-oriented services allow future modules (e.g., Tele-health Bridge) to subscribe without direct coupling. |

## Logical System Architecture – (updated in v4.0)

Table 4 Logical System Architecture Table

| Tier | Logical Component | Responsibilities | Tech Choice |
| --- | --- | --- | --- |
| Client | Flutter Mobile + Web | UI, device APIs (camera, microphone), local cache, Stripe Elements, WebSocket listener, localization framework for English (multilingual support deferred to future) | Dart / Flutter |
| Edge | Amazon CloudFrontWAF | TLS termination, SPA hosting, DDoS & OWASP rules | CloudFront, AWS WAF |
| API Gateway | REST & WebSocket endpoints | Routing, JWT validation (Cognito), request throttling | Amazon API Gateway |
| BFF (Service Mesh) | Spring Boot API- BFF | Aggregates downstream calls for mobile performance | ECS Fargate (Java 17) |
| Domain Micro- services | User-Service, Billing-Service, Scheduling- Service, Communication-Service, Analytics- Service, Trigger-Detection Service. | Each owns its schema; publishes Kafka topics | Spring Boot -> ECS Fargate |
| Data | Relational DB, Document DB, Time-series DB, Object Storage | RDS (PostgreSQL), DynamoDB, Timestream, S3 | Managed AWS |
| Integration | Stripe, Fitbit, Nest, FCM/APNs, USPS Informed Delivery | External REST / Webhooks | HTTPS, JWT mutual-TLS |
| (NEW) AI Monitoring | Amazon AIOps | Monitor the output of the DeepSeek AI to ensure compliance with safety requirements. | AWS |
| Tier | Logical Component | Responsibilities | Tech Choice |
| Streaming | Event Bus (“CareBus”) | Domain events, audit trail | Amazon MSK (Kafka) |
| Analytics | Athena / QuickSight | Ad-hoc queries, dashboards | Nightly ETL via Glue-Jobs |
| Security & Ops | Cognito, KMS, IAM, CloudWatch, EventBridge | AuthN/Z, secrets, logs, scheduled jobs | AWS native |

Note. This table identifies the key architectural objectives and rationale for the CareConnect platform.

## High-Level System Architecture Diagram- (updated in v4.0)

Figure 2 High-Level System Architecture Diagram 1 (NEW)

Note. This figure provides a visual timeline of the project's milestone deadlines using a Gantt chart.

Figure 3 High-Level System Architecture Diagram 2

Note. This table identifies the key architectural objectives and rationale for the CareConnect platform.

## Architectural Rationale-(updated in v4.0)

Table 5 Architectural Rationale Table

| Concern | Design Decision | Justification |
| --- | --- | --- |
| Scalability | Stateless Spring Boot services on ECS Fargate; event-driven via Kafka (MSK). | Auto-scales by CPU or queue lag; zero server management. |
| Latency | API-BFF aggregates calls; CloudFront edge caching; WebSocket for live metrics. | Reduces mobile roundtrips; meets <300 ms UX goal. |
| Security & HIPAA | Cognito JWT, TLS 1.3, at-rest AES-256 (KMS), WAF, audit to Lake Formation. | Satisfies HIPAA/GDPR encryption and audit mandates. |
| Cost Control | Fargate spot where possible; scale-to-zero Lambda ETL; S3 tiering to Glacier. | Keep MVP hosting below $300 a month during dev. |
| Extensibility | Clean domain services; events on MSK, and Timestream for IoT expansion. | New micro-services subscribe without coupling. |
| Dev Velocity | Single Git repo, multi-module Maven; Shared DTOs; OpenAPI contracts. | Reduces cross-team merge pain; enables code-gen stubs. |

Note. This table details the logical system architecture, including component tiers, responsibilities, and technology choices.

## Runtime Flows – (updated in v4.0)

- Payment Happy-Path
Patient → API-BFF → Billing-Svc → Stripe Charge → RDS commit → Push status = “ACTIVE.”

- Real-time Vital Update
Fitbit Sync Lambda → Timestream → Analytics-Svc publishes event → WebSocket to client (<5 s).

- Nightly Batch
EventBridge 02:00 UTC trigger → Glue Job aggregates TS → summary metrics → QuickSight refresh.

- Invoice OCR & Review
Patient/Caregiver → Mobile App → API-BFF → OCR/AI-Svc → Extracted fields → Invoice-Svc stores draft → Review Screen (low-confidence fields highlighted) → Caregiver edits/approves → Final commit to RDS → Audit Log updated.

- EVV Clock-In/Clock-Out Flow
Caregiver → Mobile App (GPS + timestamp capture) → API-BFF → EVV-Svc → State Aggregator API → Acknowledgment stored in RDS → Confirmation pushed to caregiver.

- Offline Mode Sync
Patient/Caregiver → Mobile App captures invoice/clock-in data (encrypted local storage) → Device Queue → Connectivity Restored → Sync-Svc pushes batched data → OCR/EVV services process → Status updated in client app.

(The followeing were added in v4.0)

- AI Mood Detection

HTTPS -> CloudFront + WAF -> API-BFF -> AI Service -> AWS S3

- Health data & symptom tracking

Request -> HTTPS -> CloudFront/WAF -> API Gateway -> API-BFF -> User Service -> AWS S3

- Medication Management with Reminders

Patient -> API Gateway -> API-BFF -> Scheduling-Service to upsert the schedule and dosing rules in RDS -> Schedule triggered -> Notification sent

- Patient Check-In

Patient → Data Inputs → Database → Notification for Caregiver

- Voice Transcription

Patient → Device Recording → DeepSeek API → DeepSeek AI → DeepSeek API → Text Display

- Multilingual Support

Patient or caregiver selects language option → Mobile App frontend → English locale at runtime → UI refreshes with selected resources.

- Trigger Detection

Documentation module → Trigger-Detection Service → Caregiver Alert → Audit Log Update

## Technology Stack Summary – (inherited from v3.0)

Table 6 Technology Stack Summary Table

| Layer | Tech | Notes |
| --- | --- | --- |
| Front-end | Flutter 3.x (Dart 3) | Single code-base iOS/Android/Web |
| BFF & Services | Java 17, Spring Boot 3, Maven multi-module | Micrometer, Resilience4j |
| Data | RDS (Postgres 15), DynamoDB, Timestream 1.0 | Flyway migrations |
| Messaging | MSK (Kafka 3.x, TLS) | Topic per domain (billing, vitals, alerts) |
| CI/CD | GitHub Actions → AWS CodeBuild / CodeDeploy | Blue green ECS; semantic-version tags |
| Observability | CloudWatch Logs, Prometheus ECS sidecar, Grafana Cloud | Traces via AWS X-Ray |
| Security | AWS Cognito (OIDC), KMS, WAFv2, IAM-least privilege | S3 Block Public Access |

Note. This figure presents a high-level system architecture diagram showing data flow and component integration.

## Deployment Topology Highlights – (inherited from v3.0)

- All Spring services run as container images in an ECS Fargate cluster inside a private subnet; only API Gateway and CloudFront are publicly routable.

- Secrets (DB passwords, Stripe keys) are stored in AWS Secrets Manager; tasks assume

IAM roles with the least-privilege policy generated via AWS SAM.

- Observability: structured JSON logs are shipped to CloudWatch; metrics and traces are exported via OpenTelemetry to a managed Grafana workspace.

- Blue/Green deployments are orchestrated by CodeDeploy. Rollback is automatic on canary health-check failures (<2 min).

This section outlines a secure, scalable, serverless and cloud-native technical architecture for CareConnect. We will be using Amazon Web Services (AWS) to build the infrastructure and Flutter to build the user interface.

This setup is well-suited for modern web and mobile applications that require secure access control, high availability while being able to scale to zero and integrate with internal AWS services and external third-party seamlessly.

## Frontend – (updated in v4.1

CareConnect’s frontend is primarily designed for ease-of-use by both patients and caregivers, with configurable features integrated in the code to allow for user preference of the UX. The frontend will be comprised of code using Flutter and Dart, allowing for support from a wide range of platforms. The UI was designed with role-specific functionality in mind. This allows for separate features dependent on the user’s role – patient or caregiver.

The frontend provides a consistent navigation shell with role-aware menus and reusable page templates. State management supports responsive updates for documentation, scheduling, billing, and alerts while preserving usability on mobile devices.

Accessibility and performance are prioritized. Pages load within the target latency budget, apply text scaling, and provide clear validation and error messaging. Offline capture is supported for selected workflows with synchronization when connectivity is restored. A localization framework is included to support English at launch. Multilingual features are explicitly Out-of-Scope for the MVP, as documented in the Assumptions section.

Main Pages: (updated in v4.0)

- Welcome/Login page

- Patient Home Page

- Patient Symptoms & Allergies Page

- Patient Check-In Page

- Patient Medications Page

- Patient’s Report Page

- In-App Messages

- Caregiver Home Page

- Caregiver’s Schedule Page

- Caregiver’s Patient list page

- Admin panel

- Invoice Scanning Page

- Invoice Review/Payment Page

- Electronic Visit Verification Page

- Payment Page

- USPS Mail Assist Page

- Vial of Life

- Fall Detection

- Smart home Integration with Alexa

- Chatbot

- Dashboards for patients and caregivers

## Backend- (updated in v4.0)

The backend will constitute a set of AWS services for the core infrastructure and integrate external third-party resources and API(s). We will be using Terraform for infrastructure as code (IaC) management that would help to spin up, update, and take down all the resources needed in our infrastructure.

- Amazon Cognito – User Authentication and Authorization

Purpose: Manages user sign-up, sign-in, and access control.

Features:

  - Supports OAuth2.0, SAML, and OpenID Connect.

  - Integrates with API Gateway to secure endpoints.

  - Enables multi-factor authentication (MFA) and social identity providers (Google, Apple, etc.).

- Amazon API Gateway

Purpose: Act as the entry point for all requests

Features:

- Routes requests to backend services.

- Integrate with Cognito for authentication and authorization.

- Supports rate limiting, throttling, and monitoring.

- Amazon Elastic Container Service (ECS)

Purpose: Host and orchestrate containers for the application, the backend.

Features:

  - Supports Fargate for serverless type of launch

  - Integrate with Application Load Balancer (ALB) for traffic distribution

  - Scalability

  - Secure networking to block all external communications

- SpringBoot – For backend development

Purpose: Develop Rest API with Java  Features:

  - Robust and secure

  - Uses Java

  - Supports and integrates countless external technologies for all aspects.

- Amazon Relational Database Service (RDS) – Managed SQL Database Server  Purpose: Stores structured applications data.

Features:

  - Supports engines like MySQL and PostgreSQL.

  - Offers automated backups, and read replicas

  - Encrypted at rest and in transit

For CareConnect, we will be using PostgreSQL.

- Amazon S3 – for Object Storage

  - Purpose: Stores static assets like image, documents.

  - Features:

    - Cheap

    - Durable

    - Scalable

- Amazon CloudWatch – for Monitoring and Logging

    - Purpose: Provides observability into application and infrastructure

    - Features:

      - Collects logs and metrics from ECS, API Gateway, RDS.

- AWS Identity and Access Management (IAM) – Security and Permissions

  - Purpose: Manage permission between AWS services, resources, and users.

Features:

      - Enforces least privilege access (LPA)

      - ECS tasks assume IAM roles to access RDS, S3 and more

- DeepSeek AI – AI Parsing and Responses – (added in v4.0)
         Purpose: Return an AI response to a prompt created by the program code 
         Features:

- Take any given text, get an appropriate response from the AI server.

- Deal with higher level reasoning.

- USPS Informed Delivery API– (added in v4.0)
         Purpose: Help clients deal with medical-related mail deliveries.
         Features:

- AI-assisted mail reading and analysis

- Security Protocols

## Database – (inherited from v3.0)

The CareConnect database is designed to securely store and manage application data related to users, tasks, health records, and system operations. The database will ensure data integrity, support HIPAA compliance, and provide reliable access for both mobile and backend components.

Database Technology Stack:

- Database Type: Relational (SQL-based)

- Preferred Platform: PostgreSQL (hosted on AWS RDS, a cloud service)

- ORM/Access Layer: Dart packages compatible with Flutter, such as sqflite or drift for local caching if offline support is needed.

Key Database Components:

- Users Table

Stores account information for patients, caregivers, and admins. Includes authentication credentials, contact details, and role-based metadata.

- Patients Table

Contains patient-specific profiles, medical notes, emergency contacts, and linked caregiver relationships.

- Care Tasks Table

Stores both pre-defined and custom tasks related to care, such as medications, meals, and appointments, with timestamps, frequency, and completion status.

Notifications Table

Logs system-generated alerts and reminders for both patients and caregivers, tracking delivery and response status.

- Billing Table

Manages billing events, payment history, subscription status, and Stripe transaction references.

- Invoices Table

Captured medical invoices from providers.

- EVV_Visits Table

Electronic Visit Verification visit records.

- Notifications Table

Logs system-generated alerts and reminders for both patients and caregivers, tracking delivery and response status.

- Billing Table

Manages billing events, payment history, subscription status, and Stripe transaction references.

Security & Compliance Features:

- Role-based access enforced through middleware  Data encryption at rest and in transit

- Regular backups and automated failover support

- Data retention and purging policies for compliance

Scalability Considerations:

- Support for multi-tenancy for different organizations or caregiver groups

- Optimized indexes for common query patterns (e.g., task retrieval by date or caregiver)

- Future-readiness for migration to a distributed database if user volume scales

## APIs – (Updated in v4.0)

The CareConnect platform requires robust and secure API integrations to support its modular feature set. Each subsection describes the purpose, integration model, and relevant considerations for the respective API.

### Fitbit Web API

- Purpose: Retrieve heart rate and step count data from Fitbit devices.

- Authentication: OAuth 2.0

- Data Accessed: Heart rate, step count

- Platform Support: Android, iOS

- Considerations: Requires user account linking and periodic data sync.

### Apple HealthKit API

- Purpose: Retrieve heart rate and step count data on Apple Health on iOS devices.

- Authentication: Native iOS permission-based access

- Data Accessed: Heart rate, step count

- Platform Support: iOS only

- Considerations: Requires explicit user consent for each metric.

### Google Health Connect API

- Purpose: Retrieve heart rate and step count data on Android devices through a unified API for Google Fit and partner apps.

- Authentication: Android permission-based access

- Data Accessed: Heart rate, step count

- Platform Support: Android only

- Considerations: Health Connect to be installed and permitted.

### Google Smart Device Management (SDM) API

- Purpose: Interact with Google Nest smart home devices for environmental monitoring.

- Authentication: OAuth 2.0

- Data Accessed: Motion events, device status, live camera availability

- Platform Support: Cloud-based

- Considerations: Must be carefully managed for privacy.

### Alexa Smart Home Skill API

- Purpose: Enable control and monitoring of Alexa-compatible smart home devices.

- Authentication: OAuth 2.0

- Data Accessed/Controlled: Device state, control directives.

- Platform Support: Cloud-based

- Considerations: Integration requires Smart Home Skill certification and user account linking.

### OpenFDA API

- Purpose: Retrieve official medication information using NDC codes.

- Authentication: None (public API)

- Data Accessed: Medication name, dosage, manufacturer, instructions

- Platform Support: Web-based

Considerations: Used to auto-populate medication entries from scanned NDC codes.

### DeepSeek AI API (added in v4.0)

- Purpose: Make queries to the DeepSeek AI servers

- Authentication: http bearer authentication

- Data Accessed: DeepSeek AI’s response to the given prompt.

- Platform Support: Anything with internet.

- Considerations: Charges a small fee for massive amounts of transactions, requires internet access, rate of response is variable based on traffic.

### USPS Informed Delivery API

Purpose: Use artificial intelligence and image scanning to provide assistance to patients viewing and reading their mail in CareConnect.

- Authentication: OAuth2.0, JWT Token.

- Data Accessed: Email, text, imaging, physical mail.

- Platform Support: Web-based. Apple iOS. Android.

- Considerations: Used for in-app mail analysis. HIPPA compliant with set-up and execution.

## AI Services – (updated in v4.0)

### Purpose and User Flow – (updated in v4.0)

- Users can enter messages via voice, which will be automatically transcribed into text. The user will have the chance to review the created text. Further, the voices of different users will be recognized by the AI voice recognition.

- AI will assist in the maintenance and creation of calendar events and appointments.

- User mood will be detected and recorded via AI analysis of the user’s voice.

- Interface with smart home monitoring systems.

- Patients use the “Ask” feature in the app to type or ask questions about their treatment plans or symptoms. These questions are used as the basis for a document search, which will provide sources for any statements it makes.

- Utilize DeepSeek, a HIPAA/GDPR-compliant LLM, to power the “Ask” feature for patients to pose personalized care questions.

- If a patient’s question looks risky or outside the AI’s safe zone, it’s held back for a real clinician to review before the patient sees it.

### Technical Architecture

#### Frontend Integration

- Secure REST calls from the mobile app to an AI Gateway.

#### AI Gateway

- Handles authentication/authorization, rate limiting, and request routing to DeepSeek.

#### DeepSeek Service

- Retrieves patient context from the backend, invokes LLM, and returns structured JSON answers.

#### Review & Escalation

- Flag any high-risk queries for human clinician review before delivering to the patient.

#### Security and data Protection

- Encryption: All PHI (Personal Health Information) in transit and at rest must use AES-256 encryption, and TLS 1.2+ for network calls.

- Data Minimization: Only supply DeepSeek with the minimal necessary attributes (e.g., plan ID, symptom entries) and discard logs after compliance retention periods.

- Audit Logging: Maintain immutable logs of AI interactions, including timestamps, user IDs, and query transcripts, stored in a secure, access-controlled ledger.

#### Compliance and Governance

- Privacy by Design: Embed compliance controls into each component (e.g., tokenization, PII redaction) to ensure HIPAA and GDPR adherence from day one.

- Human-in-the-Loop: Escalate any AI responses outside predefined safety envelopes to clinicians for manual approval.

- Periodic Review: Conduct quarterly risk assessments and model audits to validate compliance and performance.

#### Summary and Future Enhancements

##### AI Service Summary

- The ability for patients to easily and efficiently get the information they need without having to wait for a human caregiver that might not be available is something that could significantly increase patient quality of life. The AI integration piece for the ‘Ask’ function is a great way to achieve this, though takes some careful planning to ensure we are implementing strict security best practices and making sure we keep the quality-of-care high through human review when necessary.

##### Future Enhancements

- Potential avenues for further AI integration would be automated care alerts for caregivers based on aggregating information on vitals and medicine reception by the patients and running LLM inference against the data to find anomalies. These anomalies would be reported back to caregivers in real-time as they are found to ensure the quickest triage and remedy.

## Hosting – (inherited from v3.0)

### Cloud Deployment Model

- Adopt API Gateway as the entry point for all client requests, enforcing authentication and throttling.

- Use AWS Fargate with ECS to run containerized services (backend API, AI Gateway) in a serverless-managed cluster, eliminating server management overhead.

### Containerization and Orchestration

- Docker Images: Build stateless microservices, each with immutable Docker images stored in Amazon’s ECR (Elastic Container Registry)

- ECS Task Definitions: Define CPU/memory limits and Amazon IAM (Identity and Access Management) roles per task, ensuring least-privilege access to AWS resources.

- Auto Scaling: Configure ECS Service Auto Scaling to adjust desired tasks based on CPU/memory metrics.

### Serverless-First & Scale-to-Zero

Leverage AWS Lambda to achieve scale-to-zero and cost efficiency.

### Security and Reliability

- Containers live inside a private network segment with no direct public access, and outbound calls go through controlled gateways.

- We protect the front door with a web firewall and standard defenses against denial-of-service attacks.

- Data backups and multi-zone deployments ensure that, even if one data center goes down, the service stays up, and data stays safe.

## Security

Security is a core principle in the design and operation of the CareConnect application. Our approach integrates industry best practices to protect sensitive health information and ensure compliance with regulations such as the Health Insurance Portability and Accountability Act (HIPAA) and the General Data Protection Regulation (GDPR). Security measures are implemented across all components of the system, including the user interface, backend services, data storage, APIs (Application Programming Interfaces), and AI (Artificial Intelligence) features, through a combination of encryption, access controls, monitoring, and secure development practices.

### Data Protection

#### Encryption

- All Personal Health Information (PHI) is encrypted both when stored and during transmission, using the strong industry encryption standards of AES 256 for data being stored and TLS 1.2 for any data in transit between systems.

#### Data Minimization

- We limit the collection and use of personal data to what is necessary for providing services. Identifiable information is replaced with tokens where possible, and logs are anonymized to protect user privacy.

### Authentication and Access Control

#### User Authentication

- Secure authentication mechanisms are in place, supporting multi-factor authentication (MFA) and social login options, to verify user identities effectively.

#### Role-Based Access Control (RBAC)

- Access to system features and data is determined by user roles (such as patient, caregiver, or administrator), ensuring users can only access information pertinent to their responsibilities.

#### Principle of Least Privilege

- Access permissions are granted based on the minimum necessary access required for a user's role, reducing potential security risks, and will be managed through AWS IAM (Identity & Access Management).

### Secure APIs

#### API Gateway Protection

- All API traffic is managed through AWS API Gateway, a secure gateway that enforces rate limiting and input validation to prevent misuse and attacks.

### Infrastructure Hardening

#### Network Isolation

- System components are deployed within isolated virtual networks, preventing direct exposure to the internet and reducing the attack surface.

#### Web Application Firewall (WAF)

- A firewall is in place to protect against common web exploits such as SQL injection and cross-site scripting (XSS).

#### Firewall Rules

- Strict firewall configurations control traffic between system components, allowing for only necessary communication.

### Monitoring and Logging

#### Real-Time Monitoring

- CareConnect will leverage the capabilities of AWS CloudWatch to monitor threats to the system continuously and actively, monitoring administrators whenever an anomaly is detected.

#### Audit Logging

- All critical actions, including logins, data modifications, and AI interactions, are recorded in secure and unchangeable logs to support auditing and compliance efforts.

### Vulnerability Management

#### Interval Scanning

  - The system undergoes routine scans to identify and address vulnerabilities in both backend and mobile components.

#### Automated Patching

  - Security patches are applied automatically to system components as part of our continuous integration and deployment processes, ensuring timely updates.

### Compliance Measures

#### Regulatory Compliance

- The system is designed with privacy and security considerations from the outset, aligning with HIPAA and GDPR requirements.

#### Data Retention and Deletion

- Personal data is retained only as long as necessary for service provision, and users can request data deletion in accordance with legal guidelines.

# Project Deliverables- (updated in v4.0)

The CareConnect platform is continuously evolving to meet the needs of patients, caregivers, and healthcare providers. The following deliverables represent both existing milestones and new integrations. Deliverables are categorized as in progress or new depending on their development stage.

Core Deliverables (In Progress)

- Fully functional mobile apps (Caregiver & Patient)

  - A modern and well-designed, developed, and tested mobile application intended to enhance the overall patient/caregiver experience.

  - Current status: In Progress.

- Web dashboard for caregivers

  - Caregivers (professional or family) will have the ability to add new patients, view a list of existing patients, and connect in one-on-one sessions.

  - Current status: In Progress.

- Admin panel for operations

  - Ability for admins to add, edit, and delete entries in the system database.

  - Provides access to all features of the platform UI.

  - Current status: In Progress.

- Technical documentation

  - Developer comments embedded throughout the codebase for readability.

  - GitHub README updated with instructions, dependencies, and integration notes.

  - Current status: In Progress.

- User manuals & onboarding guides

  - Includes descriptions of all UI pages and functionality.

  - Designed to ensure smooth adoption by caregivers, patients, and administrators.

  - Current status: In Progress.

### Upcoming Milestones (New Deliverables)

- CareConnect Invoice-Bill Assistant (New)

  - Provides automated invoice generation, billing summaries, and patient-friendly cost breakdowns.

- Invoice/Payment Support (New)

  - Expansion of the Invoice-Bill Assistant to handle full payment processing and integration with financial systems.

- CareConnect Mail Delivered Assistant (New)

  - Scans, organizes, and summarizes incoming patient/caregiver mail into an accessible dashboard.

- CareConnect Home Monitoring Integration (New)

  - Enables integration with home monitoring devices for real-time patient vitals tracking.

- Smart Home Integration (New)

  - Expansion of CareConnect Home Monitoring to integrate with broader smart home cameras for patient fall detection.

- AI Mood Module (In Progress)

  - Leverages sentiment analysis to assess and monitor patient emotional well-being through caregiver-patient interactions.

- Medication Management Feature (In Progress)

  - Allow patients and caregivers to manage prescriptions, reminders, refill alerts, and dosage tracking.

- Check-In Prototype (In Progress)

  - A lightweight daily check-in system to collect mood, vitals, and wellness updates.

- Telemedicine Call Transcription Module (New, High-Value)

  - Real-time transcription of telemedicine calls, enabling searchable visit notes and enhanced caregiver documentation.

- Medical Visit Notetaker Engine (New, High-Value)

  - Automatically summarizes key visit details, decisions, and follow-up items for both patients and caregivers.

- ADA-Compliant Mail Digest Feature (New, High-Value)

  - Creates accessible digests of incoming messages, fully compliant with ADA standards for readability.

- ASL Conversion Interface (New, High-Value)

  - Converts speech and text to American Sign Language (ASL) animations or visual outputs for accessibility.

# Risk & Mitigation- (updated in v4.0)

## Risk Probability Matrix - (inherited from v3.0)

Table 7 Risk Probability Matrix Table

|  | Probability |  |  |  |
| --- | --- | --- | --- | --- |
| Impact | 1 = High (80% ≤ x ≤ 100%) | 2 = Medium High (60% ≤ x ≤ 80%) | 3 = Medium Low (30% ≤ x ≤ 60%) | 4 = Low (0% ≤ x ≤ 30%) |
| A = High (Rating 100) | 100 –Very High Exposure | 80 –Very High Exposure | 60 –High Exposure | 30 – Moderate Exposure |
| B = Medium (Rating 50) | 50 – High Exposure | 40 – Moderate Exposure | 30 – Moderate Exposure | 15 – Low Exposure |
| C = Low (Rating 10) | 10 – Low Exposure | 8 – Low Exposure | 6 – Low Exposure | 3 – Very Low Exposure |

## Risk Identification, Probability, and Mitigation- (updated in v4.1)

## Table 8 Risk Probability and Mitigation Table

| Risk |  |  | Probability |  | Impact | Score |  | Mitigation Strategy |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HIPAA compliance failure (data mishandling, misconfigured AWS) |  |  | 3 |  | A | 90 |  | Regular audits, legal reviews, use HIPAA-eligible AWS services, and enforce encryption. |  |  |
| Failure to integrate third-party APIs (Stripe, Fitbit, Nest, Zoom) |  |  | 3 |  | A | 80 |  | Implement fallback APIs, use versioned SDKs, and add error-handling. |  |  |
| Team members not completing assigned tasks |  |  | 1 |  | A (High) | 60 |  | Maintain open communication through daily stand-ups in team chat and reassign work quickly. |  |  |
| Team members lack the required technical skills (Flutter, AWS, HIPAA compliance) |  |  | 1 |  | B (Medium) | 50 |  | Allocate training, peer programming, and provide resource libraries. |  |  |
| AI misuse/errors (mood detection misclassification, Ask AI wrong answers, incorrect ASL translation, inaccurate note creation) |  |  | 2 |  | B | 40 |  | Add disclaimers, human-in-the-loop review, and audit datasets quarterly. |  |  |
| Client scope changes mid-project |  |  | 2 |  | B | 40 |  | Moderate probability and moderate exposure. We will use the change process to record changes in scope and plan accordingly. |  |  |
| Trigger detection generates false positives (alerting on safe phrases) or false negatives (missing critical phrases) |  |  | 2 |  | B | 40 |  | Provide caregiver-configurable phrase lists, allow custom phrases, perform testing with varied transcripts, and log alerts for audit review. |  |  |
| Mobile device fragmentation & OS compatibility issues (Android/iOS versions) |  |  | 3 |  | B | 30 |  | Test on real devices & emulators; phased rollout; crash analytics monitoring. |  |  |
| Poor user adoption or usability issues (patients/caregivers find the app confusing) |  |  | 3 |  | B | 30 |  | Usability testing, simplified UI/UX, multilingual support, and video tutorials. |  |  |
| Lawsuit risk (before deployment) |  |  | 1 |  | C | 6 |  | Minimal concern until public release. |  |  |

| Risk; Probability; Impact; Score; Mitigation Strategy. HIPAA compliance failure (data mishandling, misconfigured AWS); 3; A; 90; Regular audits, legal reviews, use HIPAA-eligible AWS services, and enforce encryption.. Failure to integrate third-party APIs (Stripe, Fitbit, Nest, Zoom); 3; A; 80; Implement fallback APIs, use versioned SDKs, and add error-handling.. Team members not completing assigned tasks; 1; A (High); 60; Maintain open communication through daily stand-ups in team chat and reassign work quickly.. Team members lack the required technical skills (Flutter, AWS, HIPAA compliance); 1; B (Medium); 50; Allocate training, peer programming, and provide resource libraries.. AI misuse/errors (mood detection misclassification, Ask AI wrong answers, incorrect ASL translation, inaccurate note creation); 2; B; 40; Add disclaimers, human-in-the-loop review, and audit datasets quarterly.. Client scope changes mid-project; 2; B; 40; Moderate probability and moderate exposure. We will use the change process to record changes in scope and plan accordingly.. Trigger detection generates false positives (alerting on safe phrases) or false negatives (missing critical phrases); 2; B; 40; Provide caregiver-configurable phrase lists, allow custom phrases, perform testing with varied transcripts, and log alerts for audit review.. Mobile device fragmentation & OS compatibility issues (Android/iOS versions); 3; B; 30; Test on real devices & emulators; phased rollout; crash analytics monitoring.. Poor user adoption or usability issues (patients/caregivers find the app confusing); 3; B; 30; Usability testing, simplified UI/UX, multilingual support, and video tutorials.. Lawsuit risk (before deployment); 1; C; 6; Minimal concern until public release.. |  |  |  |  |
| --- | --- | --- | --- | --- |

# Budget Estimate-(updated in v4.0)

## Labor Cost- (updated in v4.0)

The main component for the budget cost of the CareConnect project will be the cost of labor per team member. An estimate of labor costs can be viewed in the table below:

Table 9 Budget Estimate for Total (Teams A-D) Labor Costs

| Phases | Cost |
| --- | --- |
| Milestone: 1 | $ 48,800.00 |
| Milestone: 2 | $ 59,600.00 |
| Milestone: 3 | $ 170,400.00 |
| Milestone: 4 | $ 27,800.00 |
| Total Cost | $ 306,600.00 |

### Team Labor Cost Breakdown by Milestones- (updated in v4.1

#### Milestone 1: Weeks 1-3

Table 10 Team Labor Cost Breakdown Milestone 1

| Role | Team A | Team B | Team C | Team D | Hrs/Week | Rate/Hr | Total Across Teams |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager |  | Alondra |  |  | 10 | $ 80.00 | $ 3,200.00 |
| Project Planner/Lead | Sadina | Sukhmeet Khalar | Amber Young | Sudarshan Neupane | 60 | $ 75.00 | $ 18,000.00 |
| Business Analyst | Mitchell | Izabela | Sameen Shahbaz | Matthew Wilson | 60 | $ 45.00 | $ 10,800.00 |
| UI/UX Designer | Mickey | Yara | Isabel Santiago | Seth Jones | 20 | $ 50.00 | $ 4,000.00 |
| Technical Architect | Tevin | William Rave | Kparkay Togba | John Miggins | 20 | $ 70.00 | $ 5,600.00 |
| Technical Writer | Team |  | Nana |  | Chris Nmezi |  | Team |  | 40 |  | $ 45.00 | $ 7,200.00 |
| *Hours a distrubted amoungst every person in each role, i.e. 15 for each team lead totaling 60 hours |  |  |  |  |  |  |  |  |  |  | Total: | $ 48,800.00 |

#### Milestone 2: Weeks 4-6

Table 11 Team Labor Cost Breakdown Milestone 2

| Role | Team A | Team B | Team C | Team D | Hrs/Week | Rate/Hr | Total Across Teams |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager |  | Alondra |  |  | 10 | $ 80.00 | $ 3,200.00 |
| Project Planner/Lead | Sadina | Sukhmeet Khalar | Amber Young | Sudarshan Neupane | 20 | $ 75.00 | $ 6,000.00 |
| Technical Architect | Tevin | William Rave | Kparkay Togba | John Miggins | 90 | $ 70.00 | $ 25,200.00 |
| Software Developer | Matthew | Team | Mark Senkus | Aj Kelon Harris | 50 | $ 60.00 | $ 12,000.00 |
| Q/A Test Engineer | Lidia | Thomas | Abel Tabesse | Alexandra Bomani George | 40 | $ 60.00 | $ 9,600.00 |
| Technical Writer | Team | Nana | Chris Nmezi | Team | 20 | $ 45.00 | $ 3,600.00 |
|  |  |  |  |  |  | Total: | $ 59,600.00 |

#### Milestone 3: Weeks 7-9

Table  Team Labor Cost Breakdown Milestone 3

| Role | Team A | Team B | Team C | Team D | Hrs/Week | Rate/Hr | Total Across Teams |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager |  | Alondra |  |  | 30 | $ 80.00 | $ 9,600.00 |
| Project Planner/Lead | Sadina | Sukhmeet Khalar | Amber Young | Sudarshan Neupane | 60 | $ 75.00 | $ 18,000.00 |
| Technical Architect | Tevin | William Rave | Kparkay Togba | John Miggins | 60 | $ 70.00 | $ 16,800.00 |
| Software Developer | Matthew, Team | Team | Mark Senkus, Team | Aj Kelon Harris | 420 | $ 60.00 | $ 100,800.00 |
| Q/A Test Engineer | Lidia | Thomas | Abel Tabesse | Alexandra Bomani George | 60 | $ 60.00 | $ 14,400.00 |
| Technical Writer | Team | Nana | Chris Nmezi | Team | 60 | $ 45.00 | $ 10,800.00 |
|  |  |  |  |  |  | Total: | $ 170,400.00 |

#### Milestone 4: Weeks 10-12

Table  Team Labor Cost Breakdown Milestone 4

| Role | Team A | Team B | Team C | Team D | Hrs/Week | Rate/Hr | Total Across Teams |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager |  | Alondra |  |  | 5 | $ 80.00 | $ 1,600.00 |
| Project Planner/Lead | Sadina | Sukhmeet Khalar | Amber Young | Sudarshan Neupane | 10 | $ 75.00 | $ 3,000.00 |
| Technical Architect | Tevin | William Rave | Kparkay Togba | John Miggins | 10 | $ 70.00 | $ 2,800.00 |
| Software Developer | Matthew | Team | Mark Senkus | Aj Kelon Harris | 60 | $ 60.00 | $ 14,400.00 |
| Q/A Test Engineer | Lidia | Thomas | Abel Tabesse | Alexandra Bomani George | 10 | $ 60.00 | $ 2,400.00 |
| Technical Writer | Team | Nana | Chris Nmezi | Team | 20 | $ 45.00 | $ 3,600.00 |
|  |  |  |  |  |  | Total: | $ 27,800.00 |

## Materials Cost-(inherited from v3.0)

Given this project is to be completed in the scope of a capstone course, team members will be responsible for their hardware technology used for development (laptops, keyboards, mice, etc.).

Thus, hardware costs are estimated to be $0.

## Infrastructure Cost – (updated in v4.0)

This subsection converts the target technical architecture (Section 6) into a quantified operating expense forecast so that project sponsors can gauge cash burn and approve the required AWS spend-limit. The estimate follows a “bottom-up, usage-based” methodology commonly used in U.S. SaaS cost modelling:

- Reference Architecture Mapping – Each logical component (API Gateway, Fargate tasks, RDS, MSK, S3, etc.) is mapped to its corresponding billable SKU in the AWS Pricing

Catalog (Amazon Web Services, 2024).

- Sizing Assumptions – Workload drivers—concurrent users, API calls, data-ingest volume, and retention—are derived from the SRS (user counts) and the Performance NFRs (<200 ms p99, 99.9 % SLA). Conservative headroom (+20 %) is applied to prevent cost overruns during load spikes.

- Unit-Price Collection – April 2025 on-demand (or free-tier/spot) prices for the us-east-1 region were pulled from the AWS Pricing API and validated against the AWS Pricing Calculator worksheets archived in project SharePoint (rev 1.2). Stripe, Apple, and Google fees reference each vendor’s public tariff sheet (Stripe, 2025; Apple Developer Program, 2025).

- Estimation Technique – For recurring services, costs are projected as

MRC = Unit Price × Monthly Usage Qty

Project Burn = MRC × 3 months (11-week MVP + 1-week hyper-care)

One-off items (app-store enrollments, TLS certificates) are treated as Cap-Ex charges in 	Month 1.

- Contingency Allocation – A 10% buffer is added to cover unseen data-egress or long– retention growth, consistent with company FP&A guidelines for cloud projects.

- Validation – Numbers were peer-reviewed by the CloudOps FinOps analyst and reconciled against the previous quarter’s reference workloads to ensure no line item deviates by >15 % from historical benchmarks.

The resulting figure ≈ USD 1.3 K for the entire MVP period—represents less than 1 % of total project budget, affirming the decision to use managed, serverless AWS services rather than selfhosted infrastructure (Stripe, Inc., 2025; Apple Inc., 2025).

| # | Service | Sizing Assumption | Unit Price* | Monthly Qty | MRC USD |
| --- | --- | --- | --- | --- | --- |
| 1 | ECS Fargate (CPU+RAM) | 4 tasks × (0.25 vCPU / 0.5 GB) avg 50 % util | 0.04048 $/vCPUh0.004445 $/GB-h | 288 vCPU-h288 GB-h | 16 |
| 2 | API Gateway REST | 3 M API calls/mo | 3.50 $ per 1 M | 3 | 11 |
| 3 | API Gateway WebSocket | 500 active conn. · 720 h | 0.25 $/M mins | 216 000 mins | 54 |
| 4 | AWS Cognito MAU | 6 000 unique users | 0.0055 $/MAU | 6 000 | 33 |
| 5 | Amazon RDS- PostgreSQL | db.t4g.medium Multi-AZ | 0.101 $/h × 730 h | 730 | 74 |
| 6 | RDS storage & I/O | 40 GB gp3 + 3 M I/O | 0.115 $/GB-mo + 0.20 $/M I/O | – | 8 |
| 7 | Amazon DynamoDB | 15 GB + 2 M WCUs/RCUs | 1.25 $/GB + 1.25 $/M WCU | – | 25 |
| 8 | Amazon Timestream | 20 GB ingestion + 200 M queries | 0.50 $/GB + 0.02 $/M | – | 20 |
| 9 | Amazon MSK Serverless | 100 GB in/out; 50 GB-h storage | 0.11 $/GB-in/out + 0.01 $/GB-h | – | 16 |
| 10 | S3 Standard + PUT/GET | 200 GB data + 1 M ops | 0.023 $/GB + API | – | 8 |
| 11 | CloudFront Data Out | 400 GB/mo | 0.085 $/GB (Tier 1) | – | 34 |
| 12 | AWS Lambda (Glue ETL) | 1 M req, 80 GB-s | 0.20 $/M + 0.00001667 $/GB-s | – | 4 |
| 13 | CloudWatch & X-Ray | 50 GB logs, 5 M traces | 0.50 $/GB + 5 $/M | – | 30 |
| Subtotal – AWS Recurring |  |  |  |  | 333 $/month |

Table  Infrastructure Cost Table

### AWS Core Services – (inherited from v3.0)

* Prices: AWS public on-demand rates as of April 2025, us-east-1; Fargate uses spot where idle utilization <35 %.

### Third-party / One-time Fees- (updated in v4.0)

Table  Fees Table

| Service | Type | Cost USD |
| --- | --- | --- |
| Apple Developer Program | Annual | 99 |
| Google Play Console | One-time | 25 |
| Stripe – Standard Plan | Usage-based | < 0.3 % per txn (pass-through) |
| Sectigo TLS Wildcard (if not using ACM) | 1-year cert | 80 |
| Gitlab-(added in v4.0) | Monthly | 29 |

### Total Budget for MVP Phase (13 weeks ≈ 3 months)

Table  Total Infrastructure Table

| Category | Monthly | 3-Month | Notes |
| --- | --- | --- | --- |
| AWS Core (Table 1 subtotal) | 333 | 999 | uses spot + free tier credits |
| λ / Glue ETL data transfer | Incl. | Incl. | fold into AWS subtotal |
| App-store & TLS fees | — | 204 | 99 + 25 + 80 |
| Subtotal |  | 1,203 |  |
| Contingency 10 % |  | 120 | burst traffic, data-out |
| Grand Total (Infrastructure) |  | ≈ 1,320 USD |  |

### Cost-Control & Optimization Plan – (inherited from v3.0)

Table  Cost-Control Table

| Lever | Action | Expected Savings |
| --- | --- | --- |
| Compute | Keep QA & Feature branches on smaller 0.25 vCPU tasks; auto-stop dev DB nights/weekends. | 15–20 % |
| Storage | Lifecycle S3 uploads >90 days to Glacier Instant; compress CloudWatch logs with AWS Logs Insights. | 5–7 % |
| Traffic | Enable CloudFront Origin Shield; consolidate API endpoints to reduce DNS lookups. | 3–5 % |
| Reserved Instances | Purchase 1-yr RDS Standard RI after MVP proves stable. | 35–40 % on DB layer |
| Spot | Maintain Fargate spot capacity providers with ondemand fallback. | 50–60 % on compute bursts |

### Alignment to Financial Policies

- Cap-Ex vs. Op-Ex. All spend is Op-Ex (pay-as-you-go), aligning with U.S. GAAP guidance for cloud-service costs (ASC 350-40).

- Cost Recognition. Expenses booked monthly via consolidated AWS invoice to Cost Center IT-R&D-CareConnect.

- SOX Controls. AWS accounts integrated with enterprise AWS Organizations. Detailed billing reports exported to an immutable S3 bucket for audit.

- HIPAA Compliance Fees. AWS BAA services carry no surcharge; Stripe’s PCI scope

remains with the vendor. No additional license cost foreseen.

### Budget Summary for Project Plan- (updated in v4.0)

Table  Budget Summary Table

| Line Item | Amount (USD) |
| --- | --- |
| Labor Cost (Section 9.1) (updated in v4.0) | $ 306,600.00 |
| Materials Cost (Section 9.2) | 0 |
| Infrastructure (9.3) | $1,320.00 |
| Risk Buffer (9.4) – (added in v4.0) | $ 3,066.84 |
| Total Project Budget – (updated in v4.0) | ≈ $310,986.84 |

The infrastructure allocation represents <1 % of total project spends, validating a serverless, payas-you-go strategy that keeps capital exposure minimal while meeting security and compliance requirements.

## Risk Buffer – (added in v4.0)

The total cost of this project is estimated to be $306,684.00. Adding a 10% buffer will give protection against over constraining the project.

Total in Risk Buffer = $3,066.84

# Roles & Responsibilities – (updated in v4.0)

For successful planning and execution of CareConnect (Fall 2025), clear identification of roles and responsibilities is essential. Since this is a 12-week capstone course multiple team members will take on dual or supporting roles to ensure timely completion of deliverables. Role assignments align with the PMP Plan RACI, SRS ownership, and milestone deliverables.

## Roles

Table  Roles & Responsibilities Table with Assigned Team Members

| Role | Team Members | Responsibilities |
| --- | --- | --- |
| Client | Dr. Assadullah Roy Gordon Ashley Wayne | Provide product requirements and feedback on product progress |
| Project Mentor | Roy Gordon Ashley Wayne Alireza Minagar | - Advise student team members - Review deliverables upon request and provide constructive feedback |

| Role | Team Members | Responsibilities |
| --- | --- | --- |
| MS Teams & GitHub Mentor | Robert Wilson | - Act as Admin role for - MS Teams and - GitHub resources - Schedule MS Teams meetings - Provide GitHub - access for course |
| Class Project Manager | Alondra Vega Pacheco | - Organize team project progress for all teams - Provide updates to course professor |
| Team Lead | Sudarshan Neupane Sadina Wagner [Team A] | - Organize project team deliverables - Provide project progress to Class Project Manager - Provide team member communications |
| Technical Lead/Architect | John Miggins Alex Osterneck [Team A] Matthew Pingel [Team A] | - Design project architecture - Lead developers in implementation |
| Lead Software Developer | Aj Keion Harris Tevin Adams [Team A] | - Lead Software Developer members in implementing functional code - Meet with Technical Lead/Architect to ensure components are implemented correctly |
| Lead UI/UX Designer | Seth Jones Michael Maloney [Team A] | - Lead UI/UX Designers - Confer with leads of UI designs - Help design wireframes for product mockups |
| Lead Tester | Alexandra Bomani George Lidia Rocha [Team A] | - Create test matrix for unit, integration, and system testing - Confer with leads of test plans - Work with testers to create tests and perform tests against product |
| Business Analyst/Scheduler | Mitchell Lord [Team A] | - Elicit/document requirements - Own SRS 2 & 7; co-own 3 & 6 with BE; - Maintain backlog & schedule agendas/minutes; traceability; change control. |

## RACI Matrix

Table  RACI Matrix Table Key:

- R – Responsible

- A – Accountable

- C – Consulted

- I - Informed

| Task | Client | Project Manager | Team Lead | Business Analyst | Technical Lead/Architect | Developer | UI/UX Designer | Tester |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone 1 |  |  |  |  |  |  |  |  |
| Project Plan | C | A | R | C | C | I | I | I |
| SRS | I | C | C | A | C | R | R | I |
| Milestone 2 |  |  |  |  |  |  |  |  |
| TDD | I | C | C | C | A | R | I | C |
| Task | Client | Project Manager | Team Lead | Business Analyst | Technical Lead/Architect | Developer | UI/UX Designer | Tester |
| Software Test Plan | C | I | C | C | I | I | I | A |
| Mobile App Development | I | I | C | I | C | A/R | C | C |
| Web Service Development | I | I | C | I | A | R | I | C |
| Infrastructure setup | I | C | C | I | A | R | I | C |
| UI/UX Design | I | I | C | I | I | C | A/R | I |
| 3rd-Party Device Integration | I | I | C | I | A | R | I | C |
| 3rd- Party Billing Integration | I | I | C |  | A | R | I | C |
| Deployment | I | C | C | I | A | R | I | C |
| Milestone 3 |  |  |  |  |  |  |  |  |
| Test Cases | I | I | C | C | I | I | I | A/R |
| Product Testing | I | I | C | I | I | R | I | A |
| Programmer Guide | I | I | C | I | C | A | I | I |
| Deployment and Operations Guide | I | C | C | I | A | R | C | C |
| Milestone 4 |  |  |  |  |  |  |  |  |
| User Guide | C | C | C | A | I | I | R | I |
| Test Report | I | I | C | I | I | I | I | A |
| Product Delivery | I | A | R | C | C | R | I | C |

# Monitoring and Reporting – (updated in v4.0)

## Objectives

The need for monitoring and reporting comes from having to track project progress as well as team performance. The continuous tracking of these aspects of the project will allow for the earliest indication of deviation from the schedule and project goals as well as allowing for corrective actions to be taken sooner. The data used in the reporting will be transparent and continuously updated to allow project stakeholders to have the most accurate information to make informed decisions.

- GitHub + Excel Master Tracker for progress vs plan.

- Weekly dashboards (variance, defects, pass/fail rates).

- Peer reviews, CI/CD gates, HIPAA compliance checks.

- Decision Tracker integrated for scope traceability.

## Intra-Team Monitoring and Reporting

The CareConnect team will set up structured monitoring and reporting mechanisms to ensure timely progress, scope alignment, and quality assurance. Task ownership, completion, and status updates will also be tracked using GitHub Projects and synchronized with a Microsoft Excel Master Tracker document. Weekly dashboards will highlight planned vs. actual progress, hours logged, and quality metrics (e.g., defect counts, test pass/fail rates). Variance commentary will be documented, and unresolved variances will be escalated to the Risk Register.

- Weekly Sprint Reviews – Each week, the team will review completed tasks, discuss blockers, and reprioritize backlog items.

- Decision Tracker Integration – All major project decisions will be logged with rationale, alternatives, and impact, ensuring traceability across PMP, SRS, TDD, and subsequent deliverables.

- CI/CD Quality Gates – In the CI/CD pipeline, automated test suites will execute with each commit. Dashboards will be used to record results and assess coverage patterns, defect recurrence, and acceptance criteria compliance. If something goes wrong, escalations and variance reports will be started.

## Project Communications

### Internal Meetings

The team will meet internally twice a week to discuss task status, quality assurance progress, and upcoming milestones. The Master Tracker shall retain a record of these meetings, as well as any actions that were discussed.

### Internal-External Meetings

Weekly meetings with external stakeholders, such as faculty, mentors, and product owners, will be held with the goal of demonstrating incremental functionality in an isolated testing environment, updating progress, and validating requirements. For traceability, comments will be recorded and entered into the Decision Tracker.

### Cross-Team Meetings

Cross-team communications will occur on an as-needed basis to address dependencies (e.g., shared architecture, DevOps pipelines, or client interactions). All outcomes from cross-team discussions will be summarized in the Decision Tracker and reported back to internal stakeholders.

### Quality and Risk Reporting

Testing results will be connected to project reporting. A Defect Log will track the severity, status, and resolution time of all defects. The difference between expected and actual quality metrics will be summarized in weekly dashboards. Assumptions that are invalidated during testing are escalated to the Risk Register for proactive mitigation.

## Quality Plan

The CareConnect team will ensure that quality is built into all project activities and deliverables through structured reviews, automated checks, and compliance monitoring. Quality management will focus on process quality, product quality, and regulatory adherence.

- All major deliverables (PMP, SRS, TDD, Test Plan) will undergo peer review for clarity, accuracy, and completeness. Issues will be logged in the Decision Tracker and tracked to closure.

- Incremental deliverables will be validated against customer expectations and verified against requirements. Automated CI/CD quality gates will include unit testing, static code analysis, and security scans.

- A Defect Log will track severity, ownership, and resolution time. Weekly dashboards will summarize defect trends, test coverage, and pass/fail metrics to guide corrective actions.

- Requirements will be mapped to acceptance criteria in the RTM. No deliverable will be closed until all criteria are satisfied and test evidence recorded.

- HIPAA and GDPR standards will guide data handling, encryption, and privacy. Compliance checkpoints will be conducted at each milestone.

# Assumptions - (updated in v4.0)

The following assumptions have been identified as part of the CareConnect project. Each assumption is reviewed for alignment with the defined Scope of Work (see Section 3). Where applicable, Out-of-Scope items are explicitly noted to ensure clarity. Any disproven assumptions will be escalated to the Risk Register in accordance with project quality management practices.

- Device Compatibility – It is assumed that all end-users (patients, caregivers, and administrators) will access CareConnect using modern smartphones capable of running current operating systems (iOS/Android). This assumption aligns with the Scope of Work, which excludes dedicated hardware or wearable device support in the MVP.

- Language Support – The initial release will provide English-only support, while multilingual features are deferred as Out-of-Scope for the MVP. This ensures consistent testing and usability baselines.

- Medication and Task Management – Medication lists, tasks, and documentation will be manually entered by caregivers and patients. Third-party medication management integrations are Out-of-Scope for the MVP, though API integration is included in other areas (e.g., wearables, scheduling).

- Notifications – At launch, notifications are limited to in-app alerts, as defined in the Scope of Work. Email and SMS notifications are explicitly Out-of-Scope for this release.

- User Technical Proficiency – It is assumed that some users will have limited technical skills. As advanced accessibility features (e.g., screen reader support, high-contrast modes) are Out-of-Scope for the MVP, the user interface and experience must be designed with simplicity, clarity, and minimal learning curves to accommodate a broad range of users.

- Trigger Detection – It is assumed that caregivers will provide accurate and comprehensive phrase lists. Incorrect or incomplete lists may reduce detection effectiveness.

- Users have modern smartphones.

- English-only MVP.

- In-app notifications only.

- Caregivers/patients manually input medications.

- Basic accessibility only.

# Constraints - (updated in v4.0)

The following constraints have been identified in the development of CareConnect:

- The entire development cycle for a minimal viable product must be completed within a 12-week period. This includes a fully completed product. A beta version must be ready within a 4-week period.

- Only open-source and free tools must be leveraged. There is no budget to adopt any solutions that may incur a cost.

- A serverless, scale-to-zero architecture must be prioritized to minimize costs and support elastic scaling. (updated in v4.0)

- Full regulatory compliance (HIPAA, GDPR, EVV certification, Apple App Store requirements) may not be fully met by the MVP. Certification and approval processes will be coordinated with external agencies after release. (updated in v4.0)

- CareConnect must be developed within the constraints of the chosen technology stack (Flutter/Dart for mobile, JAVA for backend services, AWS HIPAA-eligible services). (updated in v4.0)

- Accessibility standards (WCAG 2.1 AA) will only be partially met in the MVP; full compliance is deferred to future updates. (updated in v4.0)

(added in v4.0)

- Home monitoring integration is initially limited to Google Nest due to API availability. Other vendors (e.g., Arlo, Ring) cannot be supported at MVP launch.

- EVV (Electronic Visit Verification) integration cannot cover all U.S. states at launch. Each state uses different data aggregators and APIs, so the MVP will only support a limited set of states.

- Banking and payments integration is constrained to provider payment links, QR codes, and Stripe. Direct integration with every possible banking provider is infeasible.

- On-device AI models (OCR, NLP) may not run efficiently on older or low-spec devices due to CPU/RAM limitations. Performance may vary by device.

- The system will initially support only English OCR and NLP, with Spanish optional; other languages are deferred.

- Offline functionality is limited in scope. While invoices and EVV data can be captured offline, all records must sync to the server within 24 hours of reconnecting.

# Work Breakdown Structure (WBS) - (updated in v4.1)

## Structure

Table 21 Work Breakdown Structure for CareConnect Fall 2025

Note. New WBS has been created by SWEN 670 Fall 2025

An external Microsoft Project file has been included as a supplement of the overall documents for a more detailed view of the CareConnect project WBS.

Task Breakdown (Updated in v4.1)

Documentation & Patient Assistant Module: Includes transcription, speaker identification, and OCR digitization of ADA mail.

Symptom & Medication Tracking Module: CRUD operations with reminders, collaborative scheduling, and integrations with wearable devices.

Billing & Administrative Tools: OCR-based invoice processing, payment workflows, and subscription billing management.

Trigger Detection Module: Evaluates transcripted patient interactions for key phrases and escalates caregiver alerts with audit log updates.

# Change Management Procedures - (updated in v4.0)

The Change Management Procedures for CareConnect define how all changes to the project are identified, assessed, approved, implemented, and communicated. This structured process ensures that changes remain aligned with project goals while minimizing risks, costs, and disruptions.

## Change Control Process - (updated in v4.0)

The change control process follows a sequence of steps designed to capture, evaluate, and implement changes in a controlled manner:

- Change Identification

  - Any team member or stakeholder may initiate a change by completing a Change Request Form (CRF).

  - The CRF documents the nature of the change, its purpose, anticipated benefits, and expected impact on time, cost, scope, and resources.

  - Using a standard format prevents misinterpretation or omission.

- Initial Review

  - The Project Manager verifies that the CRF is complete and relevant to project objectives and scope.

  - Requests that fall outside the scope or add unnecessary overhead are filtered out at this stage.

- Impact Assessment

  - The request is evaluated by technical, financial, and operational stakeholders.

  - This assessment considers risks, resource needs, and potential impacts on quality, deliverables, schedule, and cost.

  - A detailed analysis ensures decision-makers have sufficient information before proceeding.

- Change Control Board (CCB) Approval

  - Findings from the assessment are presented to the CCB for discussion and decision.

  - The CCB votes on whether to approve, reject, or defer the request.

- Implementation Planning

  - Approved changes are integrated into the project plan.

  - Updates are made to schedules, budgets, and resources, and a detailed action plan is prepared.

- Implementation of Change

  - The project team executes the approved change according to the implementation plan.

  - Progress is monitored closely, and any issues are resolved promptly.

- Documentation and Communication

  - All approved changes are documented in the project baseline with details of who approved them and when.

  - Updates are communicated to team members and stakeholders to ensure clarity and transparency.

- Post-Implementation Review

  - Each change is reviewed after implementation to confirm that it meets objectives and does not introduce new risks or issues.

  - Lessons learned are documented for future reference.

Figure 4 Change Control Process Flow

## Change Control Board Roles - (updated in v4.0)

The Change Control Board (CCB) is responsible for evaluating and approving changes to the CareConnect project. Members represent both technical and business perspectives to ensure that decisions are balanced and well-informed.

Table  Change Control Board Members

| CCB Member | Role | Responsibilities |
| --- | --- | --- |
| Dr. Assadullah | Client | Provides final approval or rejection of changes and determines change priority |
| Roy Gordon | Client | Reviews proposed changes for alignment with business needs and goals |
| Ashley Wane | Client | Ensures user and stakeholder expectations are reflected in approved changes |
| Alireza Minagar | Client | Ensures user and stakeholder expectations are reflected in approved changes |
| Alondra Vega Pacheco | Project Manager | Coordinates CRF submissions and ensures consistency with scope, schedule, and resources |
| Sudarshan Neupane | Team Lead 1 | Confirms viability of requests before escalation and ensures efficient execution of approved changes |
| Sukhmeet Khalar | Team Lead 2 | Confirms viability of requests before escalation and ensures efficient execution of approved changes |
| Sadina Wagner | Team Lead 3 | Confirms viability of requests before escalation and ensures efficient execution of approved changes |
| Amber Young | Team Lead 4 | Confirms viability of requests before escalation and ensures efficient execution of approved changes |
|  | Technical Lead / Architect | Evaluates technical feasibility and impact on architecture and performance |
|  | Technical Lead / Architect | Identifies risks to functionality, stability, and quality |
|  | Technical Lead / Architect | Evaluates technical feasibility and impact on architecture and performance |
|  | Technical Lead / Architect | Identifies risks to functionality, stability, and quality |
| CareConnect Team Members | Business Analyst, Developers, Testers | Provide effort estimates, identify dependencies, and assess potential impacts |

## Internal Change Requests - (updated in v4.0)

Internal changes originate within the project team and may include:

- Technical Adjustments – Modifications to system design, algorithms, or structures to improve performance or resolve issues.

- Process Improvements – Adoption of new methods, tools, or technologies to increase efficiency.

- Resource Allocation – Reallocation of team members, budgets, or tools to address workload or meet deadlines.

All internal requests are submitted through a CRF, reviewed by the Project Manager, and escalated to the CCB as needed. Internal changes are communicated during sprint planning or project status meetings.

## External Change Requests - (updated in v4.0)

External changes come from outside the project team and may include:

- Client Feedback – Requests for new features, usability improvements, or design changes.

- Regulatory Compliance – Adjustments needed to meet new legal, industry, or organizational standards.

- Market Conditions – Enhancements required to stay competitive or meet emerging opportunities.

These requests are reviewed by the Project Manager, submitted to the CCB, and if approved, incorporated into the project plan with adjusted schedules and communicated to all stakeholders.

## UI/UX Wireframe Preview - (inherited from in v3.0)

A detailed discussion of the CareConnect UI/UX wireframes can be found in the CareConnect Technical Design Document. The Technical Design Document is included in the overall group of documents delivered to the intended audience.

## Change Request Form - (added in v4.0)

The official CareConnect Change Request Form (CRF) is used to initiate and document any proposed modifications to the project. This form captures the details of the change, including its description, rationale, anticipated benefits, and expected impact. The CRF ensures that all requests follow a consistent structure and are properly logged before being considered for review.

The corresponding CareConnect Change Review and Approval Form (CRAF) is available as a Word document in Microsoft Teams for reviewing the submitted change requests. The CRAF is completed by the Change Control Board (CCB) and project leadership to capture the review, impact assessment, approval or rejection decision, and any conditions placed on the change.

Once approved, the same CRAF is used to guide post-approval tracking (planned dates, assigned owners, testing approach, and communication plan) and to capture the post-implementation review. This final step ensures that the implemented change meets its intended objectives, does not introduce new risks, and provides a record of lessons learned for future reference.

Together, the CRF and CRAF provide a comprehensive record of the change management lifecycle from initiation through closure.

# Appendices - (updated in v4.0)

## Glossary of Terms

Glossary Table

| Term | Definition |
| --- | --- |
| CareConnect | This is the name of the project. It will be designed as an application to help caregivers and patients keep track of healthcare needs, such as appointments and health records. |
| UI/UX -User Interface/User Experience | Aspects of the application that will define how users experience and interact with the application. |
| User | A person utilizing the application is either the patient, caregiver, or family member using the application. |
| API’s (Application Programming Interface) | Permits systems to communicate with one another. |
| Wireframes | A preview of a visualization of how a user interface will appear. |
| KPI (Key Performance Indicator) | Indicator that helps to gauge performance and progress. |
| Flutter/Dart | Dart is the programming language that Flutter uses. Flutter is used to be able to use a single code among different applications. |
| HIPAA (Health Insurance Portability and Accountability Act) | Laws governing the protection of patient information. |
| GDPR (General Data Protection Regulation) | European regulations governing privacy and data protection. |
| Sprints | Short period where software developers work on aspects of a project. |
| Elastic Container Registry (ECR) | AWS storage for docker images. |
| Electronic Visit Verification (EVV) | A computerized system that uses smart devices to capture electronic proof of when and where a home or community-based service visit began and ended. |
| OCR (Optical Character Recognition) | Technology used to extract text and structured data from scanned documents or images. |
| NLP (Natural Language Processing) | AI techniques used to interpret, classify, or extract meaning from text data. |
| Audit Logs | Immutable records that capture all system actions, including invoice creation, payment updates, and status changes, for compliance. |
| Failover | The automatic switching to a backup system or infrastructure component in case of failure. |
| RPO (Recovery Point Objective) | The maximum targeted period in which data might be lost due to a system outage. |
| RTO (Recovery Time Objective) | The targeted duration of time within which a business process must be restored after a disruption. |
| MFA (Multi-Factor Authentication) | An authentication method requiring two or more verification factors (e.g., password + hardware token). |
| PCI DSS (Payment Card Industry Data Security Standard) | Security standards that ensure organizations that handle credit cards maintain a secure environment. |
| Stripe | A third-party payment gateway used for billing and subscription management. |
| Subscription Management | Functionality for managing recurring billing plans, payments, and account status (active, suspended, canceled). |
| Audit & Compliance | Processes ensuring adherence to laws, regulations, and policies (HIPAA, GDPR, PCI DSS). |
| Serverless Architecture | A cloud computing model where applications run without managing infrastructure, scaling automatically based on demand. |
| CI/CD (Continuous Integration / Continuous Deployment) | Automated processes for building, testing, and deploying code changes. |
| UAT (User Acceptance Testing) | Final phase of testing where end-users validate the system against business requirements. |
| Immutable Logs | Logs that cannot be altered once recorded, ensuring compliance and traceability. |
| On-Device AI | AI models that run locally on a device, enabling offline capabilities like invoice parsing and EVV clock-in/out. |
| Offline Sync | A mechanism where offline transactions are automatically synchronized with the server once connectivity is restored. |
| Caregiver | An individual providing care services, who may act as a local admin, contributor, or viewer in the app. |
| Patient | The primary recipient of care whose healthcare and billing records are managed in CareConnect. |
| Audit Trail | A chronological record of all system events, user activities, and changes to data for accountability. |

## References

AlphaSoft. (2023, August 5). Short-Term Memory System (STeMS) project plan (Version 4.0) [Project documentation]. University of Maryland Global Campus.

Amazon Web Services. (2025, April). AWS pricing catalog. https://aws.amazon.com/pricing/

Apple Inc. (2025). Apple Developer Program FAQ. https://developer.apple.com/support/programs/

CareConnect High Level Requirements (n.d.). UMGC. Care Connect High Level Requirements.docx

OpenAI. (2025). ChatGPT (May 30 version) [Large language model]. https://chat.openai.com/

PubNub. (n.d.). Configuration: Authentication key (Dart SDK API Reference). https://www.pubnub.com/docs/sdks/dart/api-reference/configuration#authentication-key

Stripe, Inc. (2025). Stripe pricing guide. https://stripe.com/pricing

U.S. Bureau of Labor Statistics. (2023, September 6). Computer and information systems managers. Occupational Outlook Handbook. https://www.bls.gov/ooh/management/computerhttps://www.bls.gov/ooh/management/computer-and-information-systems-managers.htmand-information-systems-managers.htm

U.S. Bureau of Labor Statistics. (2023, September 6). Computer programmers. Occupational Outlook Handbook. https://www.bls.gov/ooh/computer-and-information-technology/computerhttps://www.bls.gov/ooh/computer-and-information-technology/computer-programmers.htmprogrammers.htm

U.S. Bureau of Labor Statistics. (2023, September 6). Project management specialists. Occupational Outlook Handbook. https://www.bls.gov/ooh/business-and-financial/projecthttps://www.bls.gov/ooh/business-and-financial/project-management-specialists.htmmanagement-specialists.htm

U.S. Bureau of Labor Statistics. (2023, September 6). Software developers. Occupational Outlook Handbook. https://www.bls.gov/ooh/computer-and-information-technology/softwarehttps://www.bls.gov/ooh/computer-and-information-technology/software-developers.htmdevelopers.htm

U.S. Bureau of Labor Statistics. (2023, September 6). Web developers. Occupational Outlook

Handbook. https://www.bls.gov/ooh/computer-and-information-technology/web-developers.htm

Zoom Video Communications. (n.d.). OAuth for user authorized apps. Zoom Developer Platform. https://developers.zoom.us/docs/integrations/oauth/

# Appendix A: Project Decision Tracker (updated in v4.2)

This decision tracker document highlights key project decisions made throughout the lifecycle. Each decision includes the date, decision owner, rationale, and impact. The tracker helps maintain transparency and provides traceability for future reference.This tracker is included as a supporting document attached with this document.

*View in Web Mode to see entire table*

| Team | Decision ID | Date | Decision Title | Context/Background | Options Considered | Decision Made | Rationale | Status | Impact Area | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | D-001 | 8/15/2025 | Teck Stack Alignment | Choosing the cores technologies for frontend, | Option 1: Use previous Spring 2025 stack | Adopt professor’s Aug-2025 stack | Aligns with the manatory guidelines, | In Progress | Infrastructure | Professor |
| A |  |  |  | backend, loud, and infrastructure | Option 2: Adopt the professor's Fall 2025 stack. | (Flutter, Java Spring Boot, AWS Fargate/ECS, | ensuring comliance, and best practices. |  |  |  |
| A |  |  |  |  |  | Aurora MySQL/Postgres, Terraform). |  |  |  |  |
| A | D-M1-001 | 8/17/2025 | Delivery method: Hybrid plan → iterate | Balance academic artifacts with working software under tight timeline. | A) Waterfall; B) Pure Agile; C) Hybrid iterate | Use hybrid: publish PMP/RACI/Schedule in M1; deliver weekly increments with AC reviews. | Clear milestones + faster feedback; requires doc–code sync discipline. | Approved | Governance/ Process | Sadina |
| A | D-M1-002 | 8/18/2025 | SRS ownership | Prevent requirement/test gaps; AC must be human-centered and testable. | A) BA owns all; B) Split across leads; C) Sign-ups | Adopt C; reflect in RACI. | Higher-quality AC; stronger traceability; clear accountability. | Approved | Governance/ Process | Sadina |
| A | D-M1-003 | 8/18/2025 | PMP Ownership | Need single accountability for PMP doc updates and submission. | A) PL only; B) PL+PM share; C) Assign BA or QA | Assign PL (Sadina) as PMP owner with BA support for traceability. | Ensures alignment across scope/schedule/security; avoids drift. | Approved | Governance | Sadina |
| A | D-M1-004 | 8/19/2025 | Weekly Meeting Cadence | Prevent misalignment across multi-disciplinary team. | A) 1x weekly; B) 2x weekly; C) Async updates only | Adopt B: 2x weekly sync (client check-in + team working session). | Keeps tight loop with client & team; aligns with hybrid plan. | Approved | Governance/ Process | Sadina |
| A | D-M1-005 | 8/19/2025 | Assigned RACI | Confusion on who reviews vs owns caused gaps in past capstones. | A) Flat sign-up; B) Strict RACI by role; C) Hybrid w/ backup reviewer | Adopt C: Role-based RACI with assigned backups (approved 8/19). | Clarity + redundancy; ensures peer-review coverage. | Approved | Governance | Sadina |
| A | D-M1-006 | 8/20/2025 | Security & Privacy Coverage | CareConnect handles PII/PHI; must plan for HIPAA/GDPR controls early. | A) Handle later in Dev; B) Assign PL as Privacy/Security hat; C) Ad-hoc compliance | Adopt B: PL maintains Security/Privacy hat; security reqs embedded in SRS/PMP. | Builds compliance into design; no rework later. | Approved | Governance/ Process | Sadina |
| A | D-M1-007 | 8/20/2025 | Compliance Checklist (Week 2) | Risk of missing compliance in SRS draft. | A) Ignore in M1; B) Add lightweight checklist; C) Formal audit doc | Adopt B: lightweight compliance checklist tied to constraints section. | Ensures compliance is traceable but not over-burdened early. | Approved | Governance/ Process | Sadina |
| A | D-M1-008 | 8/21/2025 | Tooling Standardization | Risk of scattered repos and version drift. | A) Allow ad-hoc tools; B) Central GitHub + MS Teams + shared tracker | Adopt B: GitHub as single repo of record + Teams file locker. | Reduces confusion, supports CI/CD & AC reviews. | Approved | Process/Tools | Sadina |
| A | D-M1-009 | 8/22/2025 | Traceability Method | Requirements must map → design → tests. | A) Spreadsheet RTM only; B) JSON schema; C) Hybrid RTM+schema | Adopt C: JSON schema (lightweight) + RTM table. | Standardized format; future automation; satisfies audit. | Approved | Requirements/Quality | Sadina |
| A | D-M1-010 | 8/22/2025 | Risk Register Startup | Faculty guidance: risk mgmt is graded; need early start. | A) Wait until Dev; B) Start in M1 with seed risks | Adopt B: maintain live risk register starting Wk 2. | Early risk visibility; prevents surprises. | Approved | Risk/Process | Sadina |
| A | D-M1-011 | 8/21/2025 | Project Reporting | PMP decision on how reporting throughout the project will go. | A) Internal meetings, B) External Meetings, C) Cross Team Meetings, D) Ad-Hoc Meetings | Hybrid of all with A and B being reoccurring scheduled and C & D based on need. | Following guidance of PMP before and general team workflow so far in proejct | Approved | Governance/ Process | Mitchell |
| A | D-M1-012 | 8/21/2025 | Project Monitoring | PMP decison on how monitoring throughout the proejct will go. | A) CI/CD, B) Automated Testing and Dashboards, C) Reoccuring meetingas and reviews. | Hybrid of all with A and B autonomus and C being reoccurring and built into project reporting as well. | Following guidance of PMP before and general team workflow so far in proejct | Approved | Governance/ Process | Mitchell |
| A | D-M1-013 | 8/26/2025 | Bring the professor in | There is a lot of unclear communication between client and TL and PM. | A) Work out communication with PM B) Bring in professor to the conversation. | Team Lead attempted A but B had to be intiated after results from attempt at A | Need clear communciation of how much work the group has been doing. | Approved | Governance/ Process | Sadina |
| A | D-M2-001 | 8/31/2025 | Tasking structure for estimates | Task were initally assigned in a way where presentations were not prioritized | A) keep tasking as given by the lead intially B) Shift assignments not about the estimate presentation to later and focus on details of the techncial needs of the BNS | Team decided that B was the apporach | This is so that the early presentation material will be ready and that research can help work toward the TDD & STP | Approved | Governance/ Process | Mitchell |
| B | 1 | 8/15/2025 | Use of FlutterFlow for Mockups | Needed a rapid prototyping tool to build UI mockups quickly and demonstrate workflows to stakeholders. | 1. Build mockups manually in Figma/Sketch | Chose FlutterFlow for mockups. | Allows fast, no-code mockups, interactive prototypes, and easier iteration with stakeholders. | Completed | SRS | Team-B |
| B |  |  |  |  | 2. Use FlutterFlow |  |  |  |  |  |
| B |  |  |  |  | 3. Develop sample screens using html/css |  |  |  |  |  |
| B | 2 | 8/15/2025 | Team B bi-weekly meeting | Team B needs to have a bi-weekly meeting to discuss progress, blocked, and issues. | Wedensday and Friday were days where every member had availablity | Wed. and Monday at 8PM Eastern was selected | Team B needs to have a bi-weekly meeting to discuss progress, blocked, and issues. | Completed | Whole Project | Team-B |
| B |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |
| B | 3 | 8/22/2025 | Use of Figma Make for Mockups | FlutterFlow has a learning curve which could prevent Team B from completing the SRS | 1. Build mockups manually in Figma/Sketch | Migrate Team B mock up to Figma Make | Figma Make leverages AI to quickly generate mock ups | Completed | SRS | Team-B |
| B |  |  |  |  | 2. Use FlutterFlow |  |  |  |  |  |
| B |  |  |  |  | 3. Develop sample screens using html/css |  |  |  |  |  |
| B | 4 | 8/25/2025 | Use of PlantUML | Needed a lightweight tool to create UML diagrams (use case, class, sequence, activity) for design documentation. | 1. PlantUML | Chose PlantUML. | PlantUML allows us to source control the code for diagrams. | Completed | Whole Project | Team-B |
| B |  |  |  |  | 2. Graph.io |  |  |  |  |  |
| B |  |  |  |  | 3. Napkin.AI |  |  |  |  |  |
| B | 5 | 8/21/2025 | Meet with client | Team B needed to have a follow up meeting with the client and PO to further refine requirements. | 8/22/2025 or 8/23/2025 | 8/23/2025 | A list of questions were given to the client; the client responded to the list of questions on the morning of 8/22/2025. Team B needed additional time to review the responses and generate any additional questions so 8/23/2025 was chosen. | Completed | Whole Project | Team-B |
| B |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |
| B | 6 | 8/27/2025 | Setup time to do demo of FlutterFlow | A few memebers of Team B mentioned that they are unfaimilar with flutter and flutterflow. | One of the upcoming team sync meetings | 8/29/2025 | There is a lull between submission of MIlestone 1 and start of Milestone 2. I, Sukhmeet Khalar, thought this would be best time to do a demo/Q&A before the start of milestone 2. | InProgress | Product Development | Team-B |
| B |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |
| B | 7 | 8/8/2025-8/10/2025 | Creating generic health trackers | Professor indicate customer wanted to be able to track custom things (hygiene, diet, etc). The customer said there are about 20 things they'd like to have. A generic tracker would make the feature much easier to implement | 1. Gerenic tracker | Mix of hard coded and generic tracker | Technically creating a completly generic increases complexity. Mix of makes it easier. | Completed | Product Development | Team-B, S.K., Roy Gordon |
| B |  |  |  |  | 2. Hard coded tracker for all items customer wants |  |  |  |  |  |
| B |  |  |  |  | 3. Mix of hard coded and generic tracker |  |  |  |  |  |
| B | 8 | 8/8/2025-8/10/202 | Using Local LLM | Professor wanted teams to prefer to use Local LLMs for doing OCR, Mood Detect and other features | DeepSeek R1 API or Local LLM | Currently, local LLM but more research is being done. There are flutter packages that allow us to lazy load and use local LLMs. However there are some that require specialized LLM packages or wrappers. | There are 2 reasons for using local LLM: reduced cost and allows the care connect application to work w/ AI services when backend is not available. Another side-effect is, it allows CareConnect full control of the AI training. | Inprogress | Product Development | Team-B, S.K. |
| B |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |
| B | 9 | 8/5/2025-8/10/2025 | Video and Audio Chat Architecture | Previous cohorts have implemented in-app messaging. This years Team B has the feature to update the architecture of the current implementation and implement video and audio calling. | 1. Jitsi |  |  |  |  |  |
| B |  |  |  |  | 2. WebSocket |  |  |  |  |  |
| B |  |  |  |  | 3. WebRTC |  |  |  |  |  |
| B |  |  |  |  | 4. Serverless WebRTC |  |  |  |  |  |
| B | 10 | 9/11/2025 | In-App Messaging Integration in TDD | In-App Messaging integration only for check-in reminders. |  | Added In-App messaging only to virtual check-ins( 5.1.8 dependencies and 6.2.1 API integration note) |  | Completed | TDD (Section 5.1, Section 6.2.1) | Team-B, I.A. |
| C | 1 | 8/15/2025 | Adoption of FlutterFlow for creating UI mockups | Needed a rapid prototyping tool to build UI mockups quickly and demonstrate workflows to stakeholders. | 1. Build mockups manually in Figma/Sketch | Chose FlutterFlow for mockups. | The team required a prototyping solution that would enable quick turnaround of interface designs and allow workflow demonstrations to stakeholders. | Completed | SRS | Team-C |
| C |  |  |  |  | 2. Use FlutterFlow |  |  |  |  |  |
| C |  |  |  |  | 3. Develop sample screens using html/css |  |  |  |  |  |
| C | 2 | 8/20/2025 | Progress on deliverables will be maintained in a centralized project spreadsheet, with updates logged every week. | Required a structured way to manage tasks, dependencies, and timelines for the project deliverables. | 1. Use of MS teams | Chose MS Excel to sign up for task related to PMP and SRS and update status as work was completed. | Ensures all team members and stakeholders can see current progress in real time. | Completed | PMP/ SRS | Team-C |
| C |  |  |  |  | 2. Use of google forms |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  |  |  |
| C | 3 | 8/21/2025 | Use of Lucidchart | The team required an intuitive, web-based tool to develop UML diagrams (use case, class, sequence, and activity) for design documentation. Lucidchart was selected because it supports collaborative editing, cloud access, and easy integration with project deliverables. | 1. Draw.io | Chose Lucidchart | Lucidchart was selected as the diagramming tool because it provides a user-friendly, web-based interface, supports multiple UML diagram types, and allows real-time collaboration. Its cloud integration makes it easier to share and maintain design artifacts compared to text-based UML solutions. | Completed | SRS | Team-C |
| C |  |  |  |  | 2. PlanUML |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  |  |  |
| C | 4 | 8/27/2025 | Implementation of Change Management Forms with pre-submission reviews | Needed a simple way to collaborate together to review SRS and Project Plan sections for Team C. | 1. Create Excel file | Chose to have a review session via MS teams and shared each document and had each team member review for corrections. | The team needed a reliable way to log change requests, track approvals, and ensure consistency. During a review session held via Microsoft Teams, it was agreed that changes must be discussed collectively before updates are submitted to the SRS and Project Plan. | Completed | PMP/SRS | Team-C |
| C |  |  |  |  | 2. Use Google Form |  |  |  |  |  |
| C |  |  |  |  | 3. Use Word document |  |  |  |  |  |
| D | 1 | 8/15/2025 | Use of FlutterFlow for Mockups | Needed a rapid prototyping tool to build UI mockups quickly and demonstrate workflows to stakeholders. | 1. Build mockups manually in Figma/Sketch | Chose FlutterFlow for mockups. | Allows fast, no-code mockups, interactive prototypes, and easier iteration with stakeholders. | Completed | SRS | Team-D |
| D |  |  |  |  | 2. Use FlutterFlow |  |  |  |  |  |
| D |  |  |  |  | 3. Develop sample screens using html/css |  |  |  |  |  |
| D | 2 | 8/23/2025 | Use MS Project to create WBS | Required a structured way to manage tasks, dependencies, and timelines for the project deliverables. | 1. Use Excel for WBS | Chose MS Project to create the WBS. | Provides built-in features for scheduling, dependencies, and resource allocation. | In Progress | PMP | Team-D |
| D |  |  |  |  | 2. Use Jira/Github for planning |  |  |  |  |  |
| D |  |  |  |  | 3. Use MS Project |  |  |  |  |  |
| D | 3 | 8/19/2025 | Use of PlantUML | Needed a lightweight tool to create UML diagrams (use case, class, sequence, activity) for design documentation. | 1. Draw.io | Chose PlantUML. | Text-based UML makes version control easy, integrates well with Git, and supports multiple diagram types. | Completed | SRS | Team-D |
| D |  |  |  |  | 2. Lucidchart |  |  |  |  |  |
| D |  |  |  |  | 3. PlanUML |  |  |  |  |  |
| D | 4 | 8/20/2025 | Use of Change Management Forms | Needed a simple way to capture change requests, track approvals, and keep the process consistent. | 1. Create Excel file | Chose Google Form for change requests and Word Form for review/approval. | Easy to collect change requests online and standardize approvals with Word form. | Completed | PMP | Team-D |
| D |  |  |  |  | 2. Use Google Form |  |  |  |  |  |
| D |  |  |  |  | 3. Use Word document |  |  |  |  |  |
| D | 5 | 9/8/2025 | Gamification | Do we integrate gamification aspects to our app at this point? | 1. Yes build it as part of Features we are working on | Just document for Fall 2025 class and pass on to next cohert. | We have other core features that we need to spend time on rather than gamification | Completed | TDD | All Teams |
| D |  |  |  |  | 2. No, identify the area that can use gamification and make note of those sections and pass to next cohert. |  |  |  |  |  |
| D | 6 | 9/10/2025 | OnDevice OCR | What tool/library/api do we use to parse text from invoice? | 1. Apple Vision Kit/ Google ML Kit | Use OS native api kit | Don’t need extra overhead of adding 3rd party library or API | Completed | TDD | Team-D |
| D |  |  |  |  | 2. Tesseract |  |  |  |  |  |